|  | January |  | February |  | March |  | April |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Team X | Schools | Team X | Schools | Team X | Schools | Team X | Schools |
| Outreach | - Info Session Prep materials available - Mass mailing to prospective families - Ambassador meeting – parent leader recruitment efforts - CBO/day care tabling & presentations - Communication to waitlisted families | - Canvassing Days (opt.) w/ families and NS - Letter home to current families | - CBO/day care tabling & presentations - Communication to waitlisted families - Coordinate outreach events | - Info Sessions - Canvassing Days (opt.) w/ families and NS - Referral program | - Mass mailing to prospective families - CBO/day care tabling & presentations - Communication to waitlisted families - Coordinate outreach events - (If needed) add’l targeted outreach for schools not at goal | - Info Sessions - Canvassing Days (opt.) w/ families and NS - Referral program - Reminder letter home to current families | - (If needed) targeted outreach for schools not at goal | - Parent panels @ orientations |
| Operations | - SR hub is live on MM - 1/30 Host SR kick off meeting - Progress-to-goal tracker released - SM enhancements/ Troubleshooting - Upload Common apps to SM | - Confirm SR goals - Verify applicant preferences in SM | - Weekly updates to progress-to-goal tracker - SM enhancements/ Troubleshooting - Upload Common apps to SM | - Verify applicant preferences in SM | - Finalize SM integration with IC - Weekly updates to progress-to-goal tracker - SM enhancements/ Troubleshooting - Upload Common apps to SM | - Verify applicant preferences in SM | - Final SM app clean up | - 4/3 Input final paper applications |
| Lottery |  |  | - Prepare “lottery results” communication templates |  | - Host lottery/post-lottery training - Create SM registration doc templates - Finalize SM enrollment tracker - Coordinate lottery day of logistics | - Confirm # of lottery seats to pull - Confirm orientation dates - Indicate what registration docs are needed | - 4/1 Lottery Applications due - 4/8 Lottery takes place - Send lottery results to schools - Volunteers call lottery winners - Track initial accept/declines in SM - “Lottery results” mass mailing to families | - Track accept/declines in SM - Collect + input registration docs in SM - Robo call follow up to lottery winners |