## Master
Week 7-11 VOE Project Plan
Role in Week 7-11 | Name | Role (e.g. Principal, Dean of Students)
Overall Owner |  | suggested Principal (Dean of Students may play strong support or partner role)
Norm Master |  | suggested same as overall owner
Action Planning Facilitator |  | suggested same as overall owner
Observer/Coach |  | member of LT
Observer/Coach |  | member of LT
Observer/Coach |  | member of LT
Observer/Coach |  | member of LT
Observer/Coach |  | member of LT
Observer/Coach |  | member of LT
Operations Point |  | suggested DSO
Chief Scheduler |  | suggested Principal's Assistant or SSM
Data Collection & Entry Point Person |  | suggested Principal's Assistant or SSM or Each coach
Regional Superintendent |  | Regional Superintendent
Who [fill in with name] | Bucket | Suggested Action Step [customize as needed; bold actions required] | Suggested Due by [bold required] | Status | Notes
Principal | Roles & Responsibilities | LT meets to read and internalize the Week 7-11 AOTY Toolkit | 2015-09-10
Principal | Roles & Responsibilities | Get input from LT and RS on R&R if needed | 2015-09-10
Principal | Roles & Responsibilities | Draft Roles & Responsibilities for Week 7-11 | 2015-09-17
Principal | Roles & Responsibilities | Designate when you will train owners on their roles | 2015-09-17
Principal | Roles & Responsibilities | Determine when you will bring your LT together to share R&R and launch this work | 2015-09-17
Principal | Roles & Responsibilities | Submit Any R&R Changes to RS (including roll-out timeline) | 2015-09-17
Regional Superintendent | Roles & Responsibilities | Hold Principal accountable for submitting R&R, Approve R&R | 2015-09-24
Principal | Roles & Responsibilities | Prepare Week 7-11 VOE Launch Meeting Materials, including project plan customized with owner names, dates, and additional actions | 2015-09-24
Principal | Roles & Responsibilities | Hold Week 7-11 VOE Launch Meeting | 2015-09-24
Principal | Roles & Responsibilities | Transfer ownership of project plan mangement to Operations Point | 2015-09-24
Chief Scheduler | RS Support Plan | Schedule co-planning meeting between Overall Owner and Regional Superintendent, in addition to meeting to review Key Decisions & discuss Deliverables to date | 2015-09-17
Principal | RS Support Plan | Send documents to review to RS (Week 7-11 project plan, other relevant planning documents) | 2015-09-24
Regional Superintendent | RS Support Plan | Review Week 7-11 project plan and other optional documents | 2015-10-01
Principal | RS Support Plan | Co-Planning meeting: Finalize Regional Supt Support Plan in conjunction with RS | 2015-10-01
Principal | RS Support Plan | Submit Any RS Support Plan Changes to RS | 2015-10-02
Chief Scheduler | RS Support Plan | Work with RS's coordinator to schedule attendance at key action planning meetings, debriefs, culture walkthroughs, observations, and other interactions named in the RS Support Plan | 2015-10-02
Norm Master | Norming on Rigor, Engagement, and Pacing | Determine plan for norming | 2015-09-10
Norm Master | Norming on Rigor, Engagement, and Pacing | Determine types of video to collect for reflection | 2015-09-10
Norm Master | Norming on Rigor, Engagement, and Pacing | (if applicable) Plan LT observations schedule for norming and lesson plan review alignment | 2015-09-10
9 | Norming on Rigor, Engagement, and Pacing | Complete video collection | 2015-09-17
Principal | Norming on Rigor, Engagement, and Pacing | Draft & send agendas & pre-work for norming finalization meeting. | 2015-09-17
LT | Norming on Rigor, Engagement, and Pacing | LT meets to create (level 1-4) definitions and benchmarks for Rigor, Engagement, and Pacing - or provide input on/react to draft already in progress | 2015-09-24
Norm Master | Norming on Rigor, Engagement, and Pacing | Once definitions are finalized, ensure LT is normed; plan continuation of norming work and further efforts to pursue/maintain alignment over the summer | 2015-09-24
Norm Master | Norming on Rigor, Engagement, and Pacing | Plan for how to norm new, incoming LT members | 2015-09-24
Principal | Norming on Rigor, Engagement, and Pacing | Submit Key Lever Rating Definitions to RS | 2015-09-24
Regional Superintendent | Norming on Rigor, Engagement, and Pacing | Hold Principal accountable for submitting key lever rating definitions | 2015-09-25
Regional Superintendent | Norming on Rigor, Engagement, and Pacing | Review key lever rating definitions | 2015-10-01
Action Planning Facilitator | Observations & Data Cycle: Action Planning Cycle | Determine if any change will be made to Weekly Action Planning Cycle | 2015-09-17
Principal | Observations & Data Cycle: Action Planning Cycle | Submit Weekly Action Planning Cycle to RS | 2015-09-24
Regional Superintendent | Observations & Data Cycle: Action Planning Cycle | Hold Principal accountable for submitting Weekly Action Planning Cycle | 2015-09-25
Principal | Observations & Data Cycle: Coaching Portfolio | LT meets to finalize Week 7-11 Coaching Portfolios | 2015-09-17
Principal | Observations & Data Cycle: Coaching Portfolio | Submit Week 7-11 Coaching Portfolio to RS | 2015-09-24
Regional Superintendent | Observations & Data Cycle: Coaching Portfolio | Hold Principal accountable for submitting Week 7-11 Coaching Portfolios | 2015-09-25
Action Planning Facilitator | Observations & Data Cycle: Action Planning Cycle | Set repeatedly-do Action Planning Meeting agenda | 2015-10-01
Action Planning Facilitator | Observations & Data Cycle: Action Planning Cycle | Determine repeatedly-do Action Planning Meeting pre-work for LT | 2015-10-01
Operations Point | Observations & Data Cycle: Action Planning Cycle | Build out remainder of project plan with Action Planning Cycles | 2015-10-01
Principal & Norm Master | Observations & Data Cycle: Strategy | Determine plan for full-LT norming and culture walkthroughs throughout Week 7-11 to build coaching eye (e.g. group observation, one coach RTC's, debrief of coach's RTC choices) | 2015-09-17
Principal | Observations & Data Cycle: Strategy | Determine Observation Models (time allocation during observations) for full-LT, pair, and individual observer observation | 2015-09-17
Norm Master | Observations & Data Cycle: Strategy | Create plan for upfront LT norming on Observation Structures & Coaching Strategy, as well as ongoing norming throughout Week 7-11 observation period | 2015-09-17
Principal | Observations & Data Cycle: Strategy | Determine plan for transitioning from full-LT observations to pair observations to individual observations (e.g. triggers for this), keeping in mind how to build the skill set of newer deans | 2015-09-17
Principal | Observations & Data Cycle: Strategy | Determine baseline and tiered coaching support structures for teachers based on proficiency rating | 2015-09-17
Principal | Observations & Data Cycle: Strategy | Determine how you will decide as an LT how to allocate time to teachers - whether you will use the snowball strategy (recommended) to focus on moving cusp teachers, or another strategy | 2015-09-17
LT | Observations & Data Cycle: Strategy | LT meets to norm on Observation Models & Coaching Strategy, Structure, and Allocation | 2015-09-17
Principal | Observations & Data Cycle: Strategy | Submit to any changes to RS Coaching Strategy, Structure, and Allocation based on guidance and deliverables shared during All Leader Training session on Real Time Coaching | 2015-09-24
Regional Superintendent | Observations & Data Cycle: Strategy | Hold Principal accountable for submitting Coaching Strategy, Structure, and Allocation | 2015-09-25
Principal | Observations & Data Cycle: Teacher Support | Determine interventions your LT will use for struggling teachers | 2015-09-24
LT | Observations & Data Cycle: Teacher Support | LT meets to determine which LT member will own which interventions | 2015-09-24
Operations Point | Observations & Data Cycle: Teacher Support | In conjunction with Principal, create schedule for interventions | 2015-10-01
Principal &/or Operations Point | Observations & Data Cycle: Teacher Support | Create plan for tracking attendance and following up with LT coaches and the teacher if a teacher did not attend | 2015-10-01
Principal | Observations & Data Cycle: Teacher Support | Create plan for monitoring interventions to determine their effectiveness, including allocating time to discuss intervention effectiveness and problem solving in weekly structures | 2015-10-01
LT | Observations & Data Cycle: Action Planning Cycle | LT observes 100% of teachers, engaging in coaching and debriefs | Suggested Mon |  | Weekly
LT | Observations & Data Cycle: Action Planning Cycle | LT observes 100% of teachers, engaging in coaching and debriefs | Suggested Tues |  | Weekly
LT | Observations & Data Cycle: Action Planning Cycle | LT observes 100% of teachers, engaging in coaching and debriefs | Suggested Wed |  | Weekly
LT | Observations & Data Cycle: Action Planning Cycle | LT submits data into Week 7-11 data tool (Walkthrough Tool) | Suggested Wed EOD |  | Weekly
LT | Observations & Data Cycle: Action Planning Cycle | LT individually analyzes data (in observations pairs, if applicable) | Suggested Thurs Noon |  | Weekly
LT | Observations & Data Cycle: Action Planning Cycle | LT completes pre-work prior to Weekly Action Planning Meeting (in observations pairs, if applicable), submits to Action Planning Facilitator | Suggested Thurs Noon |  | Weekly
Action Planning Facilitator | Observations & Data Cycle: Action Planning Cycle | Action Planning Facilitator reviews submitted pre-work and prepares for Action Planning Meeting | Suggested Thurs EOD |  | Weekly
LT | Observations & Data Cycle: Action Planning Cycle | LT Meets: Weekly Action Planning Meeting | Suggested Thurs EOD |  | Weekly
Action Planning Facilitator | Observations & Data Cycle: Action Planning Cycle | Complete tracker for teacher proficiency and interventions during Action Planning Meeting | SuggestedThurs EOD |  | Weekly
Principal | Observations & Data Cycle: Action Planning Cycle | Submit teacher proficiency and intervention tracker to RS | SuggestedThurs EOD |  | Weekly
Regional Superintendent | Observations & Data Cycle: Action Planning Cycle | Hold Principal accountable for submitting teacher proficiency and intervention tracker | SuggestedThurs EOD |  | Weekly
LT | Observations & Data Cycle: Action Planning Cycle | Using decisions reflected in your teacher proficiency and intervention tracker, plan your upcoming week of coaching and interventions for each teacher in your portfolio | Suggested Fri |  | Weekly
LT | Observations & Data Cycle: Action Planning Cycle | Screenshot your calendar for the upcoming week showing coaching allocations, send to Principal | Suggested Fri |  | Weekly
Principal | Observations & Data Cycle: Action Planning Cycle | Hold coaches accountable for sending screenshots of calendars showing coaching allocations | Suggested Fri |  | Weekly
Regional Superintendent | Observations & Data Cycle: Action Planning Cycle | Hold Principal accountable for submitting teacher proficiency and intervention tracker | Suggested Fri |  | Weekly