## Master
Week 6 VOE Project Plan
Role in Week 6 | Name | Role (e.g. Principal, Dean of Students)
Overall Owner |  | suggested Principal (Dean of Students may play strong support or partner role)
Norm Master |  | suggested same as overall owner
Action Planning Facilitator |  | suggested same as overall owner
Observer/Coach |  | member of LT
Observer/Coach |  | member of LT
Observer/Coach |  | member of LT
Observer/Coach |  | member of LT
Observer/Coach |  | member of LT
Observer/Coach |  | member of LT
Common Picture Scorecard Owner |  | suggested Dean of Students
Operations Point |  | suggested DSO
Chief Scheduler |  | suggested Principal's Assistant or SSM
Data Collection & Entry Point Person |  | suggested Principal's Assistant or SSM or Each coach
Regional Superintendent |  | Regional Superintendent
Who [fill in with name] | Bucket | Suggested Action Step [customize as needed; bold actions required] | Suggested Due by [bold required] | Status | Notes
Principal | Roles & Responsibilities | LT meets to read and internalize the Week 6 AOTY Toolkit | 2015-05-22
Principal | Roles & Responsibilities | Get input from LT and RS on R&R if needed | 2015-05-22
Principal | Roles & Responsibilities | Draft Roles & Responsibilities for Week 6 | 2015-05-22
Principal | Roles & Responsibilities | Designate when you will train owners on their roles | 2015-05-29
Principal | Roles & Responsibilities | Determine when you will bring your LT together to share R&R and launch this work | 2015-05-29
Principal | Roles & Responsibilities | Submit R&R to RS (including roll-out timeline) | 2015-06-01
Regional Superintendent | Roles & Responsibilities | Hold Principal accountable for submitting R&R, Approve R&R | 2015-06-01
Principal | Roles & Responsibilities | Prepare Week 6 VOE Launch Meeting Materials, including project plan customized with owner names, dates, and additional actions | 2015-06-04
Principal | Roles & Responsibilities | Hold Week 6 VOE Launch Meeting | 2015-06-05
Principal | Roles & Responsibilities | Transfer ownership of project plan mangement to Operations Point | 2015-06-05
Principal | RS Support Plan | Determine who will drive ownership of the Regional Superintendent Support Plan (RS or Principal) | 2015-06-19
Principal | RS Support Plan | Consult with RS to determine when to meet to share Key Decisions & discuss deliverables to date | 2015-07-03
Chief Scheduler | RS Support Plan | Schedule co-planning meeting between Overall Owner and Regional Superintendent, in addition to meeting to review Key Decisions & discuss Deliverables to date | 2015-07-03
Principal | RS Support Plan | Send documents to review to RS (Week 6 project plan, other relevant planning documents) | 2015-07-20
Regional Superintendent | RS Support Plan | Review Week 6 project plan and other optional documents | 2015-07-23
Principal | RS Support Plan | Co-Planning meeting: Finalize Regional Supt Support Plan in conjunction with RS | 2015-07-31
Principal | RS Support Plan | Submit RS support plan to RS | 2015-08-03
Regional Superintendent | RS Support Plan | Hold Principal accountable for submitting Regional Superintendent Support Plan | 2015-08-03
Chief Scheduler | RS Support Plan | Work with RS's coordinator to schedule attendance at key action planning meetings, debriefs, culture walkthroughs, observations, and other interactions named in the RS Support Plan | 2015-08-10
Principal | VOE: On-Task Behavior, Scholar Habits, & Classroom Climate | Determine plan for creating Vision of Excellence for On-Task Behavior, Scholar Habits, and Classroom Climate. (Note that the Classroom Climate portion is newer and may require a different process than norming on the student outputs.) | 2015-05-26
Principal | VOE: On-Task Behavior, Scholar Habits, & Classroom Climate | Determine plan for reflecting on 14-15 student outputs in preparation of creating the student outputs portion of the VOE | 2015-05-26
Norm Master | VOE: On-Task Behavior, Scholar Habits, & Classroom Climate | Determine plan for creating the Classroom Climate portion of the VOE (video collecion, observations, combination, etc.) | 2015-05-26
Norm Master | VOE: On-Task Behavior, Scholar Habits, & Classroom Climate | Determine types of video to collect for reflection on 14-15 student outputs | 2015-06-01
Norm Master | VOE: On-Task Behavior, Scholar Habits, & Classroom Climate | (if applicable) Determine types of video to collect for norming on the Classroom Climate vision | 2015-06-01
Norm Master | VOE: On-Task Behavior, Scholar Habits, & Classroom Climate | (if applicable) Plan LT observations schedule for norming on the Classroom Climate vision | 2015-06-01
Operations Point | VOE: On-Task Behavior, Scholar Habits, & Classroom Climate | Create video collection plan for reflection on 14-15 student outputs & norming on the VOE | 2015-06-01
Operations Point & Norm Master | VOE: On-Task Behavior, Scholar Habits, & Classroom Climate | Complete video collection while school is in session for reflection on 14-15 student outputs & norming on the VOE | 2015-06-10
Principal | VOE: On-Task Behavior, Scholar Habits, & Classroom Climate | Draft & send agendas & pre-work for VOE finalization meeting. | 2015-06-11
LT | VOE: On-Task Behavior, Scholar Habits, & Classroom Climate | LT meets to complete reflection on 14-15 student outputs (optional template in toolkit) - or provide input/react to draft already in progress | 2015-06-12
LT | VOE: On-Task Behavior, Scholar Habits, & Classroom Climate | LT meets to create definitions and benchmarks for proficiency on Time on Task, Scholar Habits, and Classroom Climate - or provide input on/react to draft already in progress | 2015-06-12
Norm Master | VOE: On-Task Behavior, Scholar Habits, & Classroom Climate | Once VOE is finalized, ensure LT is normed on the VOE; plan continuation of norming work and further efforts to pursue/maintain alignment over the summer | 2015-06-19
Norm Master | VOE: On-Task Behavior, Scholar Habits, & Classroom Climate | Plan for how to norm new, incoming LT members on the VOE | 2015-06-19
Principal | VOE: On-Task Behavior, Scholar Habits, & Classroom Climate | Submit VOE to RS | 2015-06-19
Regional Superintendent | VOE: On-Task Behavior, Scholar Habits, & Classroom Climate | Hold Principal accountable for submitting VOE for On-Task Behavior, Scholar Habits, and Classroom Climate | 2015-06-19
Regional Superintendent | VOE: On-Task Behavior, Scholar Habits, & Classroom Climate | Review VOE for On-Task Behavior, Scholar Habits, and Classroom Climate | 2015-06-26
Norm Master | Norming on Teacher Taxonomy Skill | Determine plan for LT norming on teacher taxonomy skill | 2015-05-22
Norm Master | Norming on Teacher Taxonomy Skill | (if applicable) Determine when and how the LT will observe together before school lets out to norm on teacher taxonomy skills | 2015-05-22
Principal | Norming on Teacher Taxonomy Skill | Determine how LT will collect data on current level of teacher skill so data available for returning teachers once Week 6 begins in Fall 2015 | 2015-05-22
Chief Scheduler | Norming on Teacher Taxonomy Skill | (if applicable) Schedule observations for LT before school is out to norm on teacher taxonomy skills | 2015-05-29
Operations Point & Norm Master | Norming on Teacher Taxonomy Skill | (if applicable) Create video collection plan for norming on teacher taxonomy skills - which classrooms, points of lesson, routines to capture | 2015-05-29
Operations Point & Norm Master | Norming on Teacher Taxonomy Skill | Complete video collection while school is in session for norming on teacher taxonomy skill | 2015-06-10
Principal | Norming on Teacher Taxonomy Skill | Draft & send agendas & pre-work for taxonomy skill norming meeting; select video to use | 2015-06-11
LT | Norming on Teacher Taxonomy Skill | LT meets to determine indicators for teacher ratings 1-4 on each teacher taxonomy skill | 2015-06-12
LT | Norming on Teacher Taxonomy Skill | (if applicable) LT observes together to norm on teacher taxonomy skill | 2015-06-12
Norm Master | Norming on Teacher Taxonomy Skill | After MVP/Narration training in June cohorts, determine whether you will name specific lesson planning expectations related to Week 6 - such as scripting MVP/Narration - and how LT will norm on those expectations and what to do if they are not met, or teachers need additional support. | 2015-06-19
Norm Master | Norming on Teacher Taxonomy Skill | After indicators are finalized for each taxonomy skill, ensure LT is normed on these indicators; plan continuation of norming workand further efforts to pursue/maintain alignment over the summer | 2015-06-19
Norm Master | Norming on Teacher Taxonomy Skill | Plan for how to norm new, incoming LT members on teacher taxonomy skills | 2015-06-19
Principal | Summer Readiness & PD Planning | Build ongoing Week 6 planning into Summer Readiness time with LT | 2015-06-19
Principal | Summer Readiness & PD Planning | Determine how Week 6 topics (VOE, Teacher Taxonomy Skill, specific lesson planning expectations) will be integrated into Summer PD Plan and differentiated based on NTT and 14-15 data on teacher skill | 2015-06-26
Principal | Summer Readiness & PD Planning | Determine how Common Picture Scorecard/Prioritized Power Routines will be integrated into Summer PD Plan | 2015-06-26
Principal | Summer Readiness & PD Planning | Finalize first draft of Summer PD Plan (Core Practice) building in roll-out of Week 6 VOE and teacher taxonomy skill, incorporating the Essentials. Submit to RS | 2015-06-30
Regional Superintendent | Summer Readiness & PD Planning | Hold Principal accountable for submitting first draft of Summer PD Plan | 2015-06-30
Regional Superintendent | Summer Readiness & PD Planning | Review Summer PD plan, provide feedback to Principal | 2015-07-10
Principal | Summer Readiness & PD Planning | Revise Summer PD plan, accounting for NTT data on new teacher skill. Submit final plan to RS | 2015-07-31
Regional Superintendent | Summer Readiness & PD Planning | Hold Principal accountable for submitting final Summer PD Plan | 2015-07-31
Principal | Summer Readiness & PD Planning | Ensure Week 6 work is built into Friday PD Plan (Core Practice) | 2015-07-31
Principal | Summer Readiness & PD Planning | Complete Week 6 Fall Adult Culture Plan (from All Leader Training session), submit to RS | 2015-08-03
Regional Superintendent | Summer Readiness & PD Planning | Review Summer PD plan, provide feedback to Principal | 2015-08-06
Principal | Observations & Data Cycle: Data Tracking | Determine how teacher rating/proficiency score information will be tracked - via google doc, or another method | 2015-07-13
Operations Point | Observations & Data Cycle: Data Tracking | In conjunction with Principal, create tracker for capturing teacher proficiency and interventions coming out of action planning meeting | 2015-07-16
LT | Observations & Data Cycle: Data Tracking | Meet to rate returning teachers on taxonomy skills | 2015-07-17
Principal | Observations & Data Cycle: Data Tracking | Determine whether you'll use the online Week 6 Data Tool (strongly recommended) or the paper version | 2015-07-20
Principal | Observations & Data Cycle: Data Tracking | Determine whether you'll track any school-specific scholar habits within the Week 6 Data Tool. | 2015-07-20
Data Collection & Entry Point Person | Observations & Data Cycle: Data Tracking | (if applicable) If using the paper version of the Week 6 Data Tool, build system for collecting the paper records and inputting them into the Data Tool | 2015-08-03
Principal &/or Operations Point | Observations & Data Cycle: Data Tracking | Train LT on how to use Week 6 Data Tool | 2015-08-03
LT | Observations & Data Cycle: Data Tracking | Rate new teachers on taxonomy skills given data coming out of NTT | 2015-08-03
Principal | Observations & Data Cycle: Data Tracking | Determine if/how collected data will be shared, and with whom | 2015-08-03
Action Planning Facilitator | Observations & Data Cycle: Action Planning Cycle | Determine Weekly Action Planning Cycle | 2015-07-20
Principal | Observations & Data Cycle: Action Planning Cycle | Submit Weekly Action Planning Cycle to RS | 2015-07-20
Regional Superintendent | Observations & Data Cycle: Action Planning Cycle | Hold Principal accountable for submitting Weekly Action Planning Cycle | 2015-07-20
Action Planning Facilitator | Observations & Data Cycle: Action Planning Cycle | Set repeatedly-do Action Planning Meeting agenda | 2015-07-20
Action Planning Facilitator | Observations & Data Cycle: Action Planning Cycle | Determine repeatedly-do Action Planning Meeting pre-work for LT | 2015-07-20
Action Planning Facilitator | Observations & Data Cycle: Action Planning Cycle | Train LT on Weekly Action Planning Cycle and related action steps each week (data entry, meeting pre-work, etc.) | 2015-08-06
Chief Scheduler | Observations & Data Cycle: Action Planning Cycle | Put Weekly Action Planning Cycle on LT calendars via invites | 2015-08-07
Operations Point | Observations & Data Cycle: Action Planning Cycle | Build out remainder of project plan with Action Planning Cycles | 2015-08-07
Principal | Observations & Data Cycle: Coaching Portfolio | Finalize 2015-16 Coaching Portfolios & Decide how teachers will be assigned to coaches for Week 6 | 2015-07-20
Principal | Observations & Data Cycle: Coaching Portfolio | LT meets to finalize Week 6 Coaching Portfolios | 2015-07-31
Principal | Observations & Data Cycle: Coaching Portfolio | Submit Week 6 Coaching Portfolio to RS | 2015-08-03
Regional Superintendent | Observations & Data Cycle: Coaching Portfolio | Hold Principal accountable for submitting Week 6 Coaching Portfolios | 2015-08-03
Operations Point or Chief Scheduler | Observations & Data Cycle: Coaching Portfolio | Assigns coach/teacher pairings in Week 6 Data Tool | 2015-08-07
Principal & Norm Master | Observations & Data Cycle: Strategy | Determine plan for full-LT norming and culture walkthroughs throughout Week 6 to build coaching eye (e.g. group observation, one coach RTC's, debrief of coach's RTC choices) | 2015-07-31
Principal | Observations & Data Cycle: Strategy | Determine Observation Models (time allocation during observations) for full-LT, pair, and individual observer observation | 2015-07-31
Norm Master | Observations & Data Cycle: Strategy | Create plan for upfront LT norming on Observation Structures & Coaching Strategy, as well as ongoing norming throughout Week 6 observation period | 2015-07-31
Principal | Observations & Data Cycle: Strategy | Determine plan for transitioning from full-LT observations to pair observations to individual observations (e.g. triggers for this), keeping in mind how to build the skill set of newer deans | 2015-07-31
Principal | Observations & Data Cycle: Strategy | Determine baseline and tiered coaching support structures for teachers based on proficiency rating | 2015-07-31
Principal | Observations & Data Cycle: Strategy | Determine how you will decide as an LT how to allocate time to teachers - whether you will use the snowball strategy (recommended) to focus on moving cusp teachers, or another strategy | 2015-07-31
LT | Observations & Data Cycle: Strategy | LT meets to norm on Observation Models & Coaching Strategy, Structure, and Allocation | 2015-07-31
Principal | Observations & Data Cycle: Strategy | Submit to RS Coaching Strategy, Structure, and Allocation based on guidance and deliverables shared during All Leader Training session on Real Time Coaching | 2015-08-03
Regional Superintendent | Observations & Data Cycle: Strategy | Hold Principal accountable for submitting Coaching Strategy, Structure, and Allocation | 2015-08-03
Principal | Observations & Data Cycle: Teacher Support | Determine interventions your LT will use for struggling teachers (Dean of Students to do thinking on this during All Leader Training) | 2015-07-31
LT | Observations & Data Cycle: Teacher Support | LT meets to determine which LT member will own which interventions (Dean of Students to do thinking on this during All Leader Training) | 2015-07-31
Operations Point | Observations & Data Cycle: Teacher Support | In conjunction with Principal, create schedule for interventions | 2015-07-31
Principal &/or Operations Point | Observations & Data Cycle: Teacher Support | Create plan for tracking attendance and following up with LT coaches and the teacher if a teacher did not attend | 2015-07-31
Principal | Observations & Data Cycle: Teacher Support | Create plan for monitoring interventions to determine their effectiveness, including allocating time to discuss intervention effectiveness and problem solving in weekly structures | 2015-07-31
LT | Observations & Data Cycle: Action Planning Cycle | LT observes 100% of teachers, engaging in coaching and debriefs | Suggested Mon |  | Weekly
LT | Observations & Data Cycle: Action Planning Cycle | LT observes 100% of teachers, engaging in coaching and debriefs | Suggested Tues |  | Weekly
LT | Observations & Data Cycle: Action Planning Cycle | LT observes 100% of teachers, engaging in coaching and debriefs | Suggested Wed |  | Weekly
LT | Observations & Data Cycle: Action Planning Cycle | LT submits data into Week 6 data tool (Culture Walkthrough Tool) | Suggested Wed EOD |  | Weekly
LT | Observations & Data Cycle: Action Planning Cycle | LT individually analyzes data (in observations pairs, if applicable) | Suggested Thurs Noon |  | Weekly
LT | Observations & Data Cycle: Action Planning Cycle | LT completes pre-work prior to Weekly Action Planning Meeting (in observations pairs, if applicable), submits to Action Planning Facilitator | Suggested Thurs Noon |  | Weekly
Action Planning Facilitator | Observations & Data Cycle: Action Planning Cycle | Action Planning Facilitator reviews submitted pre-work and prepares for Action Planning Meeting | Suggested Thurs EOD |  | Weekly
LT | Observations & Data Cycle: Action Planning Cycle | LT Meets: Weekly Action Planning Meeting | Suggested Thurs EOD |  | Weekly
Action Planning Facilitator | Observations & Data Cycle: Action Planning Cycle | Complete tracker for teacher proficiency and interventions during Action Planning Meeting | SuggestedThurs EOD |  | Weekly
Principal | Observations & Data Cycle: Action Planning Cycle | Submit teacher proficiency and intervention tracker to RS | SuggestedThurs EOD |  | Weekly
Regional Superintendent | Observations & Data Cycle: Action Planning Cycle | Hold Principal accountable for submitting teacher proficiency and intervention tracker | SuggestedThurs EOD |  | Weekly
LT | Observations & Data Cycle: Action Planning Cycle | Using decisions reflected in your teacher proficiency and intervention tracker, plan your upcoming week of coaching and interventions for each teacher in your portfolio | Suggested Fri |  | Weekly
LT | Observations & Data Cycle: Action Planning Cycle | Screenshot your calendar for the upcoming week showing coaching allocations, send to Principal | Suggested Fri |  | Weekly
Principal | Observations & Data Cycle: Action Planning Cycle | Hold coaches accountable for sending screenshots of calendars showing coaching allocations | Suggested Fri |  | Weekly
Regional Superintendent | Observations & Data Cycle: Action Planning Cycle | Hold Principal accountable for submitting teacher proficiency and intervention tracker | Suggested Fri |  | Weekly
Principal | Common Picture Scorecard | Submit Common Picture core practice to Many Minds | 2015-03-30
Common Picture Scorecard Owner | Common Picture Scorecard | Prioritize 10 or fewer "power routines" from your school's common picture | 2015-06-19
Common Picture Scorecard Owner | Common Picture Scorecard | Bring your list of prioritized power routines & the visions for those routines (from your Common Picture) to All Leader Training as pre-work for the Common Picture Scorecard session | 2015-06-23
Principal | Common Picture Scorecard | Determine how you will monitor, track progress toward, and provide teacher feedback on fidelity to prioritized common picture routines - Will you use the common picture scorecard, or another RS-vetted mechanism? | 2015-07-03
LT | Common Picture Scorecard | LT meets to determine which LT member owns which power routines | 2015-06-26
Power Routine Owners | Common Picture Scorecard | Power Routine Owners pull visions for power routines from Common Picture and draft baseline components | 2015-07-03
Common Picture Scorecard Owner | Common Picture Scorecard | Create your Common Picture Scorecard (or alternate vetted format) using visions and baseline components from routine owners. List them chronologically and by importance. Get LT approval/alignment once complete. | 2015-07-19
Common Picture Scorecard Owner | Common Picture Scorecard | Submit Common Picture Scorecard (or alternate vetted format) to RS | 2015-07-20
Regional Superintendent | Common Picture Scorecard | Hold Principal accountable for submitting Common Picture Scorecard (or alternate vetted format) | 2015-07-20
Common Picture Scorecard Owner | Common Picture Scorecard | Determine how to use Common Picture Scorecard in observations to drive common Picture fidelity. | 2015-07-20
Common Picture Scorecard Owner & Norm Master | Common Picture Scorecard | Determine norming strategy around Common Picture Scorecard use - does LT use video to norm, observations at start of school, etc.? | 2015-07-20
Common Picture Scorecard Owner | Common Picture Scorecard | Determine how Common Picture Scorecard data will be tracked, and who will input the data? | 2015-07-20
Common Picture Scorecard Owner | Common Picture Scorecard | Determine if/how/when Common Picture Scorecard data will be rolled-up and shared with teachers. | 2015-07-20
Operations Point | Common Picture Scorecard | (if applicable) Consulting with Common Picture Scorecard Owner, build tracking system for scorecard data | 2015-07-20
Operations Point | Common Picture Scorecard | (if applicable) Build out repeatedly-do system for scorecard data roll-up and share-out | 2015-07-20
LT | Common Picture Scorecard | LT meets to norm on Common Picture Scorecard strategy and align on the strategy for using it. LT commits to plan for integrating into observations, reporting out, etc. | 2015-07-20