Week 6 Arc of the Year: Key Decisions

| Bucket | Key Decision | Questions to Ask Some examples | Date | Deliverable Turned in to Reg. Supt. | Resource some links are forthcoming |
| --- | --- | --- | --- | --- | --- |
| Roles & Responsibilities | Determine Roles & Responsibilities for your team during the Week 6 Vision | - Who will fill each role during Weeks 1-6? - How will I roll this out to the LT and train them? - How will I assume ultimate ownership of the Week 6 Vision, support my LT in executing their roles, and hold all staff accountable to the vision? | 6/1 | Roles & Responsibilities | See Roles & Responsibilities section of the Week 6 Arc of the Year Toolkit |
|  | Determine how your Regional Superintendent will support your LT in achieving Week 6 goals | - Is the RS or the Principal driving ownership of the support plan? - How will the RS support LT norming and roll-out to staff during Summer PD? - How will the RS push Week 6 goals through data review, co-observations, attending action planning meetings, and principal check-ins? - How will existing RS/Principal structures help support the work, and what new touch-points should be put in place? | 8/3 | Regional Superintendent Support Plan In addition, the RS & Principal should meeting in July or August to review Key Decisions & Deliverables to date. | See Role of the Regional Superintendent section of the Week 6 Arc of the Year Toolkit |
| Norming on the Week 6 Vision of Excellence for On Task Behavior, Scholar Habits, & Classroom Climate + Norming on Teacher Skill | What is your Vision of Excellence for On Task Behavior, Scholar Habits, and Classroom Climate? | - How do we define each component of the student outputs vision? - How do we define each component of classroom climate vision? - What are the benchmarks for proficiency on these components? | 6/19 | Vision of Excellence for On Task Behavior, Scholar Habits, and Classroom Climate | - Reflection on 2014-15 Student Outputs - Time on Task Norming Questions - Scholar Habits Norming Questions - Classroom Climate Norming |
|  | When and how will you norm your LT on the Vision of Excellence for On Task Behavior, Scholar Habits, & Classroom Climate? | - Will we collect and use video from the current school year? When will we collect video? - Will we observe as an LT during the current school year? When will we observe together? - When will we build in time to check for misalignment and recalibrate? | 6/19 | Build into Project Plan | Norming Questions |
|  | When and how will you norm your LT on the Inputs, or Teacher Taxonomy Skills? | - Will we record video in the current school year and norm with our LT during the summer? Can we use the same video we are collecting for VOE norming? - Will we observe as an LT during the current school year? When will we observe together? - When will we build in time to check for misalignment and recalibrate? - What are the indicators for teacher ratings 1-4 on each teacher skill? - Will we name specific lesson planning expectations related to Week 6 – such as scripting MVP/Narration (strongly recommended)? When will LT norm on these? | 6/19 | Build into Project Plan | Taxonomy Skills |
|  | When and how will you roll out and train teachers on the VOE for On Task Behavior, Scholar Habits, & Classroom Climate, as well as Teacher Taxonomy Skill? | - How will I invest teachers in the purpose and vision of the week 6 work? - What adult culture strengths will I leverage in the week 6 work? - What does this look like in August PD? - How am I using data on known skill gaps (LT knowledge and NTT data) to target or differentiate PD? - What is the ongoing vision for Friday PD? - How do we incorporate the Essentials? - How will we roll out any specific lesson planning expectations related to Week 6 – such as scripting MVP/Narration (strongly recommended)? | After All Leader Training session | Summer PD Plan (Core Practice due 6/30) | - Week 6 Adult Culture Spring PD - MVP/Narration Training in June Cohorts - Week 6 Fall Adult Culture PD at All Leader Training |
| Observations & Data Cycle | What is our Data Collection Strategy? How will Week 6 VOE data be collected and tracked for each teacher? | - How will we track teacher proficiency and interventions coming out of action planning meetings? - How am I using LT knowledge and NTT data to rank both returning and new teachers to know their gaps? - Will we use the online AOTY data tool, or the paper tool during observations? If paper, who tracks and enters this data? - Will we track any school-specific scholar habits within the data tool? - How will the data be shared, and with whom? | 7/20 | Build into Project Plan | - Weekly Data & Action Planning Cycle - Creating a Teacher Tracking Document - Sample Teacher Tracker Google Doc |
|  | What is our Data Analysis & Action Planning Strategy? What is the weekly structure for data analysis and action planning? How will LT time be prioritized? | - Will there be beginning-of-week or daily touch-points? - When is data due from coaches? - What is the pre-work and agenda setting process prior to each meeting? - What outcomes from the action planning meeting are tracked, and how? | 7/20 | - Weekly Data & Action Planning Cycle - Weekly: Teacher Tracking Mechanism (Suggested google doc) | - Weekly Data Cycle - Action Planning Meeting Pre-work - Action Planning Meeting Agenda |
|  | What is our LT’s coaching strategy, coaching structure, and allocation of coaching loads and interventions/support? | - How will teachers be assigned to coaches: Will we allocate teachers based on full-year portfolios (recommended) or differently? - How will I structure coaching to build the capacity of my LT to be both high-impact coaches and normed with a strong culture eye? - What is our model for various types of observations: full LT, pairs, and individual, and how will we scaffold down? - What structures am I setting up to ensuring the full LT remains normed throughout Week 6? - What is the strategy for allocating LT time to teachers? - Will we use the snowball strategy of moving cusp teachers? - Will we double back on teachers or observe teachers only once/week? - What type of coaching will all teachers receive, and what is differentiated based on proficiency? - How will we ensure that all LT members prioritize coaching every week? - What is the repeatedly-do for updating my RS on how coaching allocation and portfolios are changing? - Which interventions will be used to support struggling teachers? - Which LT member will own planning and/or implementing each intervention? - What is the intervention schedule? - How will we track attendance and follow up with LT coaches if someone did not attend? - How will we monitor interventions to ensure their effectiveness? | 8/3 | Forthcoming during All Leader Training: - Coaching Portfolios - Coaching Strategy - Coaching Structure & Time Allocation | - Coaching Portfolios Guidance - Example Coaching Plan & Strategy - The Snowball Strategy - Observation/Feedback Guidance - The One Observer Model - The Two Observer Model - See Teacher Interventions section of the Week 6 Arc of the Year Toolkit |
| Common Picture Scorecard | What power routines will you prioritize, and what is the vision of excellence for these routines? | - Which routines have the greatest impact on learning time? - What is our Common Picture vision for each power routine? | 6/23 | - Common Picture - List of Prioritized Power Routines - These two items are pre-work for an All Leader Training session. | - See the Common Picture Scorecard guidance section of the Week 6 Arc of the Year Toolkit |
|  | In what order will you prioritize getting to proficient on the power routines, and what are the essential components to get to proficient? | - How many different routines does the LT want to focus on at a given time? - Which LT members own which Common Picture routines? | 7/20 | - Common Picture Scorecard | - See the Common Picture Scorecard guidance section of the Week 6 Arc of the Year Toolkit - See Sample Common Picture Scorecards in the Week 6 Arc of the Year Toolkit |
|  | How will you use the Common Picture Scorecard with teachers? | - Will we directly provide this in observations? - Will we roll up as a school-wide data point for investment or progress monitoring? - If the latter, what kind of data collection system will we put in place? How will we share this data with teachers? (frequency & medium) | 7/20 | Build into Project Plan |  |
|  | When and how will you norm your LT on the Common Picture scorecard? | - Will we collect video during the current school year? How will this fit into other video collection plans for VOE and teacher skill norming? - When will we build in time to check for misalignment and recalibrate? | 7/20 | Build into Project Plan |  |
|  | When and how will you roll out and train teachers on the Common Picture scorecard? How will you build in the Essentials? | - How will I invest teachers in the purpose and vision? - What does this look like in August PD? - What is the ongoing vision for Friday PD? | 7/20 | Build into Project Plan |  |
| Maintenance of Week 6 Vision | How effective was this part of the arc? | - What is our debrief structure? - Whose voices should be heard? - What data will we collect along the way to ensure we have an effective debrief? | Week 5 | TBD | Guidance and support tools to come. |
| Maintenance of Week 6 Vision | How will my LT monitor the coaching focus areas of the arc with continued observation, data collection, and reflection? | - What role will this play in our ongoing data analysis portions of LT Meetings? | Week 5 | TBD | Guidance and support tools to come. |