## Key
This is a sample summer program project plan from AF Brooklyn High School. We advise you follow this general timeline, and make the document live by putting these dates into your outlook calendars.
All items in blue signify high-stakes internal planning meetings
All items in black signify events and other externally facing items
All items highlighted in yellow signify AF College and Alumni Report Card Goals

## Calendar of Deliverables
|  | Check-in |  |  | Approver
|  | Communication |  |  | NS Coach
|  | Confirmation |  |  | Ops.
|  | Data share |  |  | Owner
Hype Event
ALL |  | Meeting-mandatory
Pre-College |  | Meeting-optional
Internship |  | Physical space
Growth |  | Planning/working session
Request for Ops. help
Review
|  | Submission |  |  |  | Met score card goal
|  | Workshop |  |  |  | Ready/executed on time
Rubric
Survey/feedback
Program tier | Deliverable | Type of deliverable | Date due/held by: | Date completed/held: | Executed by: | Accountability | Criteria for Success: | Notes | Resources
ALL | S.P. kick-off planning session | Planning/working session | 2012-07-23 |  | Approver | Ready/executed on time | Owner leaves meeting clear on what it means to "OWN" Summer Programs, goals, metrics, timeline, function and vision for milestone calendar, communication and planning norms. | MEETING AGENDA: Review vision document, goals and metric, project plan, repeatedly-do structures, communication norms; est. deadline for owner to create internal and external calendars of major milestones/deliverables.
ALL | S.P. planning session | Planning/working session | 2012-07-30 |  | Approver | Ready/executed on time | Owner leaves meeting prepared to submit final draft of milestones calendar; Owner leaves meeting clear on aims and agenda for hype session at orientation. | MEETING AGENDA: Review internal/external milestone calendars; plan August AF-ization orientation Summer Programs hype session
ALL | S.P. planning session | Planning/working session | 2012-08-06 |  | Approver | Ready/executed on time | Owner leaves clear on whether s/he has delivered on milestones calendar, clear on deliverables for next 6 weeks; clear on and prepared for hype session for orientation. | MEETING AGENDA: Review progress against milestones calendar; preview of next 6 weeks on milestones calendar; final prep for orientation hype session
ALL | Summer Programs hype session | Hype Event | 2012-08-22 |  | Owner | Ready/executed on time | Owner engages returning scholars to lead exciting, inspiring session that clearly communicates to students the purpose of Summer Programs, tiers, eligibility, and timelines for application and placement; students feel clear on eligibility and leave buzzing about their summers. | This should be scheduled into summer AF-ization orientation but will probably only get 10-15 minutes.
ALL | S.P. planning session | Planning/working session | 2012-08-27 |  | Approver | Ready/executed on time | Owner leaves clear on whether s/he has delivered on milestones calendar, clear on deliverables for next 6 weeks; clear on and prepared for creating high-caliber bulletin boards for Summer Programs throughout builing. | MEETING AGENDA: Review progress against milestones calendar; preview of next 6 weeks on milestones calendar; approver gives feedback re: bulletin board deisgn and content (norming for picture of excellence)
ALL | Parent newsletter announcement for Summer Programs Parent Informational Presentation #1 | Communication | 2012-08-27 |  | Owner | Ready/executed on time | The parent newsletter contains a clear, succinct invite to families to attend the September Summer Programs info session.
ALL | Summer Programs bulletin boards | Physical space | 2012-08-31 |  | Owner | Rubric | Bulletin boards score a 3 or 4 on the College Office bulletin board rubric | The vision for these (mock-ups) should be shared in advance of creation.
ALL | Letter home to parents with reminder announcement for Summer Programs Parent Informational Presentation #1 | Communication | 2012-09-03 |  | Owner | Ready/executed on time |  | A reminder letter should go home stipulating that all parents should attend drop-in Summer Programs info session from 6:30-7:30 on PR Night.
| Robo call goes out with communication for Summer Programs info session @ PR Night | Communication | 2012-09-10 |  | Owner | Ready/executed on time | Robocall is scheduled with Ops. at least 1 week in advance with clear, compelling rationale for parents for attending session.
ALL | Summer Programs Parent Informational Presentation #1 | Meeting-optional | 2012-09-13 |  | Owner | Survey/feedback | 50% of families attend the optional parent info session; attending parents score a 90%+ on the exit ticket, demonstrating understanding of the purpose, options, eligibility, timeline, and parent/student next-steps for Summer Programs. | This should coincide with a Back-to-School Night, Progress Report Night, or other event where we're asking parents to come into the building.
ALL | S.P. planning session | Planning/working session | 2012-09-17 |  | Owner | Ready/executed on time | Owner sends agenda, data, and pre-work 48 hours in advance of meeting | MEETING AGENDA: Review progress against milestones calendar; preview of next 6 weeks on milestones calendar
| Summer Programs Owner's Picture of Excellence codification document shared | Communication | 2012-09-28 |  | Owner | Ready/executed on time | Owner creates a vision document and rubrics to share with approver and consulted team members that includes all rubrics and articulates picture of excellence for: workshop and parent meeting materials, applications, teacher recommendations, personal statements, SPCA quality, interviews, etc. | The function of this is to ensure that Owner and approver have normed on standard of excellence.
ALL | S.P. planning session | Planning/working session | 2012-10-12 |  | Owner | Ready/executed on time | Owner sends agenda, data, and pre-work 48 hours in advance of meeting; specifically, owner is ready to discuss and roll out MS2 and Telluride application and selection process. | MEETING AGENDA: Review progress against milestones calendar; preview of next 6 weeks on milestones calendar; preview MS2 and Telluride selection and application process, which is norming process for application support and quality
ALL | Parent newsletter announcement for Summer Programs Parent Informational Presentation #2 | Communication | 2012-10-22 |  | Owner | Ready/executed on time | The parent newsletter contains a clear, succinct invite to families to attend the Summer Programs info session.
ALL | Summer programs interest survey for use in CRS | Submission | 2012-11-03 |  | Owner | Ready/executed on time | Owner delivers clear GoogleForm that can easily be disseminated in CRS to obtain color re: scholars' programmatic and career interests for matching | Approver will review and approve GoogleForm.
ALL | Letter home to parents with reminder announcement for Summer Programs Parent Informational Presentation #2 | Communication | 2012-11-05 |  | Owner | Ready/executed on time |  | A reminder letter should go home stipulating that all parents should attend drop-in Summer Programs info session from 6:30-7:30 on PR Night.
ALL | S.P. student panel at Friday Celebration for upper school audience | Hype Event | 2012-11-06 |  | Owner | Survey/feedback | School assembly includes a 10-15 section hyping Summer Programs
ALL | Summer Programs bulletin boards updated | Physical space | 2012-11-09 |  | Owner | Rubric | Bulletin boards are updated with list of pre-college eligible scholars based on QI GPAs and merit levels; messaging is exciting and builds suspense.
ALL | S.P. student panel at Friday Celebration for lower school | Hype Event | 2012-11-09 |  | Owner | Ready/executed on time | School assembly includes a 10-15 section hyping Summer Programs
ALL | S.P. planning session | Planning/working session | 2012-11-12 |  | Owner | Ready/executed on time | Owner sends agenda, data, and pre-work 48 hours in advance of meeting | MEETING AGENDA: Review progress against milestones calendar; preview of next 6 weeks on milestones calendar
| Robo call goes out with communication for Summer Programs info session #2 @ RC Night | Communication | 2012-11-12 |  | Owner | Ready/executed on time | Robocall is scheduled with Ops. at least 1 week in advance with clear, compelling rationale for parents for attending session.
ALL | Letter home requesting financial documents (1090,W2 for 2011) submitted to College Office by all 9th, 10th, and 11th families | Communication | 2012-11-12 |  | Owner | Ready/executed on time | Letter to go home to all families with clear 12/19/12 deadine for submission, rationale, next steps for questions, confidentiality contract | Should be submitted to Ops.
ALL | 50% of pre-approved existing programs entered in Summer Programs Program Bank | Data share | 2012-11-12 |  | Owner | Ready/executed on time
ALL | Summer Programs Parent Informational Presentation #2 at RC Night | Meeting-optional | 2012-11-15 |  | Owner | Survey/feedback | 30% of families attend the optional parent info session; attending parents score a 90%+ on the exit ticket, demonstrating understanding of the purpose, options, eligibility, timeline, and parent/student next-steps for Summer Programs. | This should coincide with a Report Card Night or other event where we're asking parents to come into the building.
ALL | Share end-QI cumulative GPA and 6-week merit avg. report for current sophomores and juniors | Request for Ops. help | 2012-11-15 |  | Ops. | Ready/executed on time | Ops. will share a clear and easy-to-use spreadsheet that shows cumulative GPA and merit avg. through the end of QI. | This data will be used to filter for pre-college eligibilty.
ALL | S.P. planning session | Planning/working session | 2012-11-19 |  | Owner | Ready/executed on time | Owner sends agenda, data, and pre-work 48 hours in advance of meeting; specifically, owner is ready to provide updates on MS2 and Telluride application and selection process; Owner is clear on timeline and picture of execellence for Summer Programs catalog. | MEETING AGENDA: Review progress against milestones calendar; preview of next 6 weeks on milestones calendar; update on MS2 and Telluride selection and application process, which is norming process for application support and quality; summer programs catalog preview; plan December pre-college hype.
ALL | S.P. planning session | Planning/working session | 2012-12-03 |  | Owner | Ready/executed on time | Owner sends agenda, data, and pre-work 48 hours in advance of meeting; specifically, owner is ready to update on MS2 and Telluride application and selection process; Owner is clear on matching process criteria and timeline and can articulate these. | MEETING AGENDA: Review progress against milestones calendar; preview of next 6 weeks on milestones calendar; update on MS2 and Telluride selection and application process, which is norming process for application support and quality; pre-college matching process preview
ALL | 100% of summer programs interest sruveys completed by 9th, 10th and 11th grade scholars | Data share | 2012-12-03 |  | Owner | Ready/executed on time | All students submit complete surveys so that we have accurate and robust data on what they want to do with their summers.
ALL | CSPA (Common Summer Program Application) shared with all CRS instructors | Communication | 2012-12-03 |  | Owner | Ready/executed on time | CSPA is shared with all CRS instructors via GoogleForms, and Owner coaches CRS instructors through how to teach completion of the application. | Lesson plans for this should be uploaded to BetterLesson for CRS.
ALL | S.P. planning session | Planning/working session | 2012-12-10 |  | Owner | Ready/executed on time | Owner sends agenda, data, and pre-work 48 hours in advance of meeting; specifically, Owner is ready to update on MS2 and Telluride applications; Owner provides preliminary matching data. | MEETING AGENDA: Review progress against milestones calendar; preview of next 6 weeks on milestones calendar; update on MS2 and Telluride selection and application process, which is norming process for application support and quality; pre-college matching process
Pre-College | Preliminary Pre-college match list shared with College Team | Data share | 2012-12-14 |  | Owner | Ready/executed on time | Owner shares a list with 2-3 matches for each pre-college eligible scholar that includes a reach and a target/solid for each scholar; list includes use of all AF partner secured spots and reflects financial fit in all cases. | Approver will provide nuanced feedback.
ALL | 100% of pre-approved existing programs entered in Summer Programs Program Bank | Data share | 2012-12-14 |  | Approver | Ready/executed on time
ALL | 100% of scholars have uploaded a current resume to Naviance | Submission | 2012-12-16 |  | Approver | Met score card goal | All resumes uploaded to Naviance; 100% of the uploaded resumes scored a 3+ on the resume rubric | Resume unit in CRS 9/10 November > December
ALL | S.P. planning session | Planning/working session | 2012-12-17 |  | Owner | Ready/executed on time | Owner sends agenda, data, and pre-work 48 hours in advance of meeting; specifically, Owner provides explanation of final matching data. | MEETING AGENDA: Review progress against milestones calendar; preview of next 6 weeks on milestones calendar; update on MS2 and Telluride selection and application process, which is norming process for application support and quality; pre-college matching process; plan pre-college dinner; plan whole-staff summer programs PD; plan January pre-college hype
ALL | All financial documents submitted to College Office by all 9th, 10th, and 11th families | Submission | 2012-12-19 |  | Owner | Met score card goal | All families share complete financial documents by deadline. | This will require a TON of chasing families down; need to get crystal clear with Ops. re: who owns which steps in this process.
ALL | Pre-College eligible scholars announced at QI Awards Night | Hype Event | 2012-12-20 |  | Owner | Ready/executed on time | Well-attended QI Awards Night includes special spotlighting of pre-college eligible scholars, highlighting their hard work and achievement and their securing this important opportunity. | Will need to coordinate schedule, hype, etc. w/ owner of QI Awards Night
Pre-College | Save the Dates go out for Pre-College Scholars Special Dinner | Communication | 2012-12-20 |  | Owner | Ready/executed on time | There must be A TON of hype around this. This should be the highlight of kids' week and should be the focal point of morning community; kids should be buzzing about it all week.
Pre-College | At least 36 spots secured at pre-college programs for top scholars | Confirmation | 2012-12-20 |  | Owner | Met score card goal | 30 spots at best-fit pre-college programs have been confirmed for the summer of 2013; these are appropriately logged in the Program Bank. | This will require persistent outreach throughout December.
Pre-College | 100% of families submit financial documentation and sign financial commitment contracts |  | 2012-12-20 |  | Owner | Met score card goal |  | Aligns to College Report Card goal: Top quartile will participate in a pre-college program or highly selective internship
Internship | 100% of internship eligible scholars have uploaded first draft resume to Naviance |  | 2012-12-20 |  | Owner | Met score card goal |  | Aligns to College Report Card goal: Top quartile will participate in a pre-college program or highly selective internship
ALL | S.P. bulletin boards updated | Physical space | 2013-01-04 |  | Owner | Rubric | Bulletin boards clearly communicate application timelines for individual program tiers, info about prospective pre-college programs, and the pre-college eligible list for 2012-13 | Includes pre-college eligible scholar list and info on specific programs, as well as blurb re: catalog
Pre-College | Secure 10-15 Network Support volunteers for each pre-college winter application workshop | Confirmation | 2013-01-04 |  | Owner | Ready/executed on time | Owner has 10-15 Network Support volunteers or other dynamic adults confirmed to support with the pre-college application process on the 4 Saturdays across January to March. | Must reach out to Network Support starting in November.
ALL | Summer Opportunities catalog published | Communication | 2013-01-04 |  | Owner | Rubric | Summer Opportunities catalog with program descriptions, dates, financial aid info, eligibility criteria, and deadines published in paper, through GoogleDocs, and shared as a PDF via email to all scholars | This is a 20+ hour project and requires researching all programs.
ALL | All summer programs parent policies finalized and uploaded to BetterLesson | Submission | 2013-01-04 |  | Owner | Ready/executed on time |  | These documents must be finalized and ready for dissemination at the pre-college mandatory parent dinner.
Pre-College | Formal invitation letters go home with logistics for Pre-College Scholars Special Dinner | Meeting-optional | 2013-01-04 |  | Owner | Ready/executed on time | This is the logistics letter to families communicating time/location/agenda and the fact that this is mandatory. All families must return this letter.
Pre-College | S.P. planning session | Planning/working session | 2013-01-07 |  | Owner | Ready/executed on time | Owner sends agenda, data, and pre-work 48 hours in advance of meeting; specifically, Owner leads planning of pre-college dinner, staff PD, and hype for month of January. | MEETING AGENDA: Review progress against milestones calendar; preview of next 6 weeks on milestones calendar; plan pre-college dinner agenda; plan staff PD; plan twice/week hype for pre-college
Pre-College | Robocall reminder to all pre-college families | Communication | 2013-01-08 |  | Owner | Ready/executed on time
ALL | Slides in breakfast rotation for pre-college eligibility and golden ticket day | Hype Event | 2013-01-09 |  | Owner | Survey/feedback
Pre-College | Mandatory pre-college dinner | Meeting-mandatory | 2013-01-10 |  | Owner | Met score card goal | Dinner is attended by 90%+ of pre-college eligible families; all matching, application support, financial aid, and matriculation and completion policies are clearly explained; attending parents score a 90%+ on the exit ticket. | Aligns to College Report Card goal: 75% of parents/families with pre-college eligible scholars will attend the introduction meeting
ALL | PD for teachers/advisors on Summer Programs process | Workshop | 2013-01-11 |  | Owner | Ready/executed on time | All teachers/advisors are clear on expectations for scholar participation in Summer Programs, norms/timeline/deadines for teacher recommendations. | Teachers will here get coached not to give recs. to scholars not on the rec. matrix.
Pre-College | S.P. planning session | Planning/working session | 2013-01-14 |  | Owner | Ready/executed on time | Owner sends agenda, data, and pre-work 48 hours in advance of meeting; specifically, Owner leads final planning of pre-college workshop #1 | MEETING AGENDA: Review progress against milestones calendar; preview of next 6 weeks on milestones calendar; plan pre-college workshop #1; the pre-work for this meeting is review/written feedback on the agenda, instructional materials, checklist templates, and/or organizational tools for the pre-college workshops. The idea is for this to be the final point of communication around the vision and logisitcs for the pre-college workshops.
Pre-College | Re-confirm all volunteers for Pre-College application workshops | Communication | 2013-01-14 |  | Owner | Ready/executed on time | Owner sends tickler to all volunteers to confirm their participation.
Pre-College | Final Pre-college match list shared with College Team | Data share | 2013-01-14 |  | Owner | Ready/executed on time | Owner shares a list with 2-3 matches for each pre-college eligible scholar that includes a reach and a target/solid for each scholar; list includes use of all AF partner secured spots and reflects financial fit in all cases. | Approver will sign off on this list during 1/21/12 check-in.
ALL | All financial documents uploaded to Naviance | Request for Ops. help | 2013-01-15 |  | Ops. | Ready/executed on time | All 2011 1090s and W2 for all families are uploaded to Naviance for 100% of 9th, 10th, and 11th grade families. | Request to Ops. made 3 months in advance.
Pre-College | S.P. planning session | Planning/working session | 2013-01-21 |  | Owner | Ready/executed on time | Owner sends agenda, data, and pre-work 48 hours in advance of meeting; specifically. Pre-work includes the lesson/workshop battle plans for pre-college workshops 1-4. | MEETING AGENDA: Internships pipeline plan; pre-college application progress update; final clarifying questions for pre-college workshops scope and sequence and materials for workshop #1 readiness
Pre-College | Pre-college application workshop #1 | Workshop | 2013-01-25 |  | Owner | Ready/executed on time | Workshop is meticulously planned; all scholars have GoogleDocs folder with materials; all volunteers are prepped and trained to support application checklist development and personal statement writing; water-tight system exists and is executed on for ensuring all scholars walk out of workshop with accurate checklists of documents, next steps, check-in times are accurate. 100% of scholars come prepared with their signed participation contracts. | WORKSHOP AGENDA: (1) Scholars presented with match programs; (2) scholars research match programs and application components for match programs; (3) scholars start personal statement tailoring and/or supplemental essays; (4) scholars develop individual checklist; (5) scholars check out with Owner
Pre-College | Pre-College application participation contract signed and returned by all pre-college parents and scholars | Submission | 2013-01-25 |  | Owner | Ready/executed on time | All pre-college families have signed and returned pre-acceptance contracts acknowledging financial responsibilities and completion requirements. | Scholars MUST bring this to Pre-College Workshop #1 in order to participate and get application support.
| S.P. planning session | Planning/working session | 2013-01-28 |  | Owner | Ready/executed on time | Owner sends agenda, data, and pre-work 48 hours in advance of meeting; specifically. | MEETING AGENDA: Internships pipeline plan; pre-college application progress update
Pre-College | Requests made for all teacher recommendations along with distribution of rec. guides and exemplars | Communication | 2013-01-28 |  | Owner | Ready/executed on time | All teachers are crystal clear on deadlines, where/when to find forms, vehicles and norms for submission, expectations for communications around clarifying questions. | Owner will coordinate this and will send Outlook invites with deadlines and 48-hour reminders to all writers.
Pre-College | Pre-college application workshop #2 | Workshop | 2013-02-01 |  | Owner | Ready/executed on time | All scholars arrive with the documents and preparation agreed upon at the prior week's session. Workshop is meticulously planned; all scholars have GoogleDocs folder with materials; all volunteers are prepped and trained to support application checklist development and personal statement writing; water-tight system exists and is executed on for ensuring all scholars walk out of workshop with accurate checklists of documents, next steps, check-in times are accurate. | WORKSHOP AGENDA: (1) Scholars presented with match programs; (2) scholars research match programs and application components for match programs; (3) scholars work on personal statement tailoring and/or supplemental essays; (4) scholars develop individual checklist; (5) scholars check out with Owner
Pre-College | Complete all pre-college one-on-one scholar meetings | Meeting-mandatory | 2013-02-01 |  | Owner | Ready/executed on time | Summer Programs Owner conducts one-on-one's to confirm scholar's enthusiasm/comfortability with placements and check in on checklists progress. | These will take 3 weeks and should probably happen during lunch. Meetings should take no longer than 10 minutes each.
ALL | QII Awards Night S.P. Hype | Hype Event | 2013-02-06 |  | Owner | Ready/executed on time | Eligibility for internships is announced; timelines for internships is announced. Parents/scholars are excited and clear on calendar for application/interviewing/placement. | Those who are submitting pre-college apps. should get shouted out again.
Pre-College | Pre-college application workshop #3 | Workshop | 2013-02-08 |  | Owner | Ready/executed on time | All scholars in attendance have a clear work plan to execute on with the help of their volunteer. 90% of scholars execute fully on their work plan for the afternoon. | WORKSHOP AGENDA: (1) Scholars walk through checklist and documents with volunteer; (2) scholars who need to work on personal statement tailoring and/or supplements do so; (3) scholars submit all materials; (4) scholars check out with Owner
ALL | 100% of scholars have submitted the CSPA (Common Summer Program Application) | Submission | 2013-02-08 |  | Owner | Ready/executed on time | 100% of scholar are systematically and supportively coached through completing a pollished application including a resume and personal statement. | The vehicle for this process is College Readiness Seminar 9 and 10; juniors complete their independently and attend drop-in workshops to get guidance and feedback. Pre-college applications for pre-college scholars will not be submitted until this is received.
ALL | S.P. planning session | Planning/working session | 2013-02-15 |  | Owner | Ready/executed on time | Owner sends agenda, data, and pre-work 48 hours in advance of meeting; specifically. | MEETING AGENDA: Internships and growth programs update; pre-college application completion review; begin prep for networking night
Internship | Confirm internship placements and number of spots with intern host sites/teams | Review | 2013-02-15 |  | Owner | Ready/executed on time | By mid-March, precise number of spots at partner sites is confirmed, thereby allowing for the Owner to strategically start matching eligible scholars.
ALL | 90% of parents/families with internship/growth opportunity eligible scholars will attend the introduction meeting |  | 2013-02-15 |  | Owner | Met score card goal |  | 90% of parents/families with internship/growth opportunity eligible scholars will attend the introduction meeting
ALL | Summer Programs Update #1 | Data share | 2013-02-15 |  | Owner | Ready/executed on time | Update is sent by email to all stake-holders with glows, grows, calendar look-ahead, and data | Content specs.: comprehensive scholar-by-scholar data on which scholars are submitting applications to which programs; comprehensive data on current eligibility for each program tier (current circa QII); % of families that have shared financial documents; % of scholars receiving 2s, 3s, and 4s on the SPCA
Internship | At least 15 different sites have agreed to internship opportunities (50 spots total secured) |  | 2013-03-01 |  | Owner | Met score card goal |  | Aligns to College Report Card goal: Top quartile will participate in a pre-college program or highly selective internship
Growth | At least 80 spots secured at growth programs |  | 2013-03-01 |  | Owner | Met score card goal |  | Aligns to College Report Card goal: 100% of scholars will participate in an approved summer opportunity
| 100% of non-top quartile scholars have uploaded at least one letter of recommendation for use in summer opportunity applications |  | 2013-03-01 |  | Owner | Met score card goal |  | Aligns to College Report Card goal: 100% of scholars will participate in an approved summer opportunity
ALL | 100% of non-top quartile scholars have uploaded a statement of interest for use in summer opportunity applications |  | 2013-03-01 |  | Owner | Met score card goal |  | Aligns to College Report Card goal: 100% of scholars will participate in an approved summer opportunity
Pre-College | Pre-college application workshop #4 | Workshop | 2013-03-08 |  | Owner | Ready/executed on time | All pre-college applications are 100% complete. | WORKSHOP AGENDA: (1) Scholars walk through checklist and documents with volunteer; (2) scholars who need to work on personal statement tailoring and/or supplements do so; (3) scholars submit all materials; (4) scholars check out with Owner
ALL | S.P. planning session | Planning/working session | 2013-03-15 |  | Owner | Ready/executed on time | Owner sends agenda, data, and pre-work 48 hours in advance of meeting; specifically. | MEETING AGENDA: Internships and growth programs update; pre-college application review and preliminary blocking for financial aid distrubtion; prep for networking night
Pre-College | 100% of pre-college applications are submitted complete and on time | Submission | 2013-03-15 |  | Owner | Ready/executed on time | The student application tracker in GoogleDocs is 100% accurate and up-to-date; 100% of applications went in on time and the Owner has sent follow-up emails and made follow-up phone calls to get verbal and/or written (preferrably written) confirmation that the applications are 100% complete. | The approver will check this.
| All pre-college application PDFs uploaded to Naviance | Submission | 2013-03-22 |  | Ops. | Ready/executed on time | Ops. team member will post PDF profiles for all applications
Pre-College | Audit of pre-college applications in Naviance | Review | 2013-03-22 |  | Approver | Ready/executed on time |  | Reviewed for completion and quality (using application and personal statement rubrics)
Pre-College | All recommendations printed, signed; Word files uploaded to Naviance | Submission | 2013-03-22 |  | Owner | Ready/executed on time | Every recommendation is wherehoused in Naviance associated with the appropriate scholar with consistent and clear file naming conventions adhered to.
Pre-College | Top quartile have uploaded two letters of recommendation for use in pre-college program applications to Naviance |  | 2013-03-29 |  | Owner | Met score card goal |  | Aligns to College Report Card goal: Top quartile will participate in a pre-college program or highly selective internship
| Summer Programs catalog updated and disseminated to AFBHS student body via air, land, sea | Communication | 2013-03-29 |  | Owner | Met score card goal | The Summer Programs catalog is updated with all internship and growth program deadlines, descriptions, and specs. And is shared via GoogleDocs, email, paper, etc. with scholars. | This is a 10-hour+ project and should commence in mid-February.
ALL | Summer Programs Update #2 | Data share | 2013-04-01 |  | Owner | Ready/executed on time | Update is sent by email to all stake-holders with glows, grows, calendar look-ahead, and data | Content specs.: comprehensive scholar-by-scholar data on which scholars submitted applications to which programs; comprehensive data on current eligibility for each program tier (current circa QII); pre-college acceptances and financial aid awards run-down to date by scholar; internship secured spots update
Pre-College | Finalize grant distribution forecasts shared | Review | 2013-04-15 |  | Approver | Ready/executed on time | With ~80% of acceptances and financial aid decisions in, College Team is able to forecast with 95% accuracy the grant amounts for individual scholars at each pre-college placement and can therefore calculate school scholarship amount. | Depends on AFBHS Summer Programs budget.
Pre-College | Ops. notified of grants distribution amounts and check requests for pre-college program invoices submitted | Request for Ops. help | 2013-04-15 |  |  |  | Ops. made aware of all checks that should be cut and mailed for pre-college invoices | Will want to get clear on internal process/timeline for communicating these requests to/with your Ops. team
Internship | 100% of eligible scholars have uploaded first draft cover letters to Naviance | Submission | 2013-04-20 |  | Owner | Met score card goal | Scholars score a 3+ avg. on their cover letters; 100% of cover letters are successfully and accurately uploaded. | Aligns to College Report Card goal: Top quartile will participate in a pre-college program or highly selective internship
ALL | S.P. planning session | Planning/working session | 2013-04-22 |  | Owner | Ready/executed on time | Owner sends agenda, data, and pre-work 48 hours in advance of meeting; specifically. | MEETING AGENDA: Internships and growth programs update; pre-college application review; blocking for financial aid distrubtion; prep for Networking Night
Internship | Scholars being considered for internships get invitations to interviewing workshop | Communication | 2013-04-26 |  | Owner | Ready/executed on time
ALL | Summer Programs Update #3 | Data share | 2013-04-29 |  | Owner | Ready/executed on time | Update is sent by email to all stake-holders with glows, grows, calendar look-ahead, and data | Content specs.: comprehensive scholar-by-scholar data on which scholars submitted applications to which programs; comprehensive data on current eligibility for each program tier (current circa QII); pre-college acceptances and financial aid awards run-down to date by scholar; internship secured spots update; internship and growth placements to date
Pre-College | Letter goes out to all pre-college families about mandatory pre-departure meeting | Communication | 2013-04-29 |  | Owner | Ready/executed on time
ALL | S.P. planning session | Planning/working session | 2013-04-29 |  | Owner | Ready/executed on time | Owner sends agenda, data, and pre-work 48 hours in advance of meeting; specifically. | MEETING AGENDA: Internships and growth programs update; pre-college pre-dept. meeting and interships orientation planning; Networking Night final planning
Pre-College | Update bulletin boards with pre-college placements | Hype Event | 2013-05-03 |  | Owner | Ready/executed on time | Summer Programs bulletin boards include a visually enticing list of all pre-college admits, their programs, and what they will be doing/studying. Board also includes information about internships, growth programs.
Pre-College | All parents have receive grant awards from AFBHS for pre-college | Communication | 2013-05-03 |  | Owner | Ready/executed on time | Grant letters stipulate family financial contribution, scholarship from AFBHS, contract for participation and completion covenants, timeline for payment.
Internship | 100% of eligible scholars have participated in interview/networking night | Data share | 2013-05-10 |  | Owner | Met score card goal | Networking Night is comprised of 30 minutes of interactive coaching on interviewing norms and best practices, 15 minutes of networking, and 45 minutes of mock interviews; 2 to 1 student to interviewer ratio is achieved through aggressive recruitment of interviewers (professionals from the community); scholars score a 3+ avg. on their final interview of the evening. | Aligns to College Report Card goal: Top quartile will participate in a pre-college program or highly selective internship
Pre-College | Robo-call reminder about Mandatory pre-college pre-departure meeting | Communication | 2013-05-13 |  | Owner | Ready/executed on time
ALL | S.P. planning session | Planning/working session | 2013-05-13 |  | Owner | Ready/executed on time | Owner sends agenda, data, and pre-work 48 hours in advance of meeting; specifically. | MEETING AGENDA: Internships and growth programs update; pre-college pre-dept. meeting and interships orientation planning
Pre-College | Parents return payment plans and participation contracts for pre-college tuition | Submission | 2013-05-13 |  | Owner | Ready/executed on time | All parents have returned financial and participation contracts in advance of pre-departure meeting, so that the meeting can effective focus solely on logistics.
Internship | Internship scholars and parents receive notification of their internships | Communication | 2013-05-15 |  | Owner | Ready/executed on time
Pre-College | Mandatory pre-college pre-departure meeting | Communication | 2013-05-16 |  | Owner | Ready/executed on time | All parents receive pre-college pre-departure logistics worksheets, which should be distributed and reviewed at the mandatory pre-college pre-departure meeting. 100% of parents leave meeting able to articulate their next steps.
Internship | 90% of parents/families with internship/growth opportunity eligible scholars will attend the matriculation meeting |  | 2013-05-30 |  | Owner | Met score card goal |  | Aligns to College Report Card goal: 90% of parents/families with internship/growth opportunity eligible scholars will attend the matriculation meeting
Pre-College | 100% of parents/families with pre-college eligible scholars will attend the matriculation meeting |  | 2013-05-30 |  | Owner | Met score card goal |  | Aligns to College Report Card goal: 100% of parents/families with pre-college eligible scholars will attend the matriculation meeting
Internship | Invitation goes out for mandatory Internship Orientation for scholars and parents | Communication | 2013-05-31 |  | Owner | Ready/executed on time
ALL | S.P. planning session | Planning/working session | 2013-06-03 |  | Owner | Ready/executed on time | Owner sends agenda, data, and pre-work 48 hours in advance of meeting; specifically. | MEETING AGENDA: Internships and growth programs update; matriculation logistics readiness check-in
ALL | Summer Programs Update #4 | Data share | 2013-06-03 |  | Owner | Ready/executed on time | Update is sent by email to all stake-holders with glows, grows, calendar look-ahead, and data | Content specs.: comprehensive scholar-by-scholar data on which scholars submitted applications to which programs; comprehensive data on current eligibility for each program tier (current circa QII); pre-college acceptances and financial aid awards run-down to date by scholar; internship secured spots update; internship and growth program placements; Summer Academy programs run-down
Internship | Update bulletin boards with internship and growth placements | Hype Event | 2013-06-03 |  | Owner | Ready/executed on time
Internship | Deadline for scholars confirming their internships with College Office | Confirmation | 2013-06-03 |  | Owner | Ready/executed on time
Pre-College | All parents return pre-college pre-departure logistics owrksheets | Submission | 2013-06-03 |  | Owner | Ready/executed on time
Pre-College | All payments submitted by pre-college families | Submission | 2013-06-03 |  | Owner | Ready/executed on time
ALL | S.P. planning session | Planning/working session | 2013-06-03 |  | Owner | Ready/executed on time | Owner sends agenda, data, and pre-work 48 hours in advance of meeting; specifically. | MEETING AGENDA: Internships and growth programs update; matriculation logistics readiness check-in
Internship | Reminder robo-call goes out for mandatory Internship Orientation for scholars and parents | Communication | 2013-06-04 |  | Owner | Ready/executed on time
Internship | Internship Orientation for scholars and parents | Meeting-mandatory | 2013-06-06 |  | Owner | Ready/executed on time
Growth | All Growth program scholars matched for application process; matches communicated to parents and parent consent obtained | Communication | 2013-06-07 |  | Owner | Ready/executed on time
Growth | All Growth program scholars placed | Confirmation | 2013-06-07 |  | Owner | Ready/executed on time | 100% of scholars who are eligible for off-campus opportunities and were not placed in pre-college/internships are placed in growth programs.
Pre-College | All travel, books, stipends arranged and confirmed with Ops. for pre-college scholars | Confirmation | 2013-06-14 |  | Owner | Ready/executed on time
Growth | All Growth program scholars' travel and logistics confirmed | Confirmation | 2013-06-14 |  | Owner | Ready/executed on time
Pre-College | 44 pre-college program spots secured |  | 2013-06-14 |  | Owner | Met score card goal |  | Aligns to College Report Card goal: Partnerships numbers will increase annually by 10% (AFBHS - 17 pre-college, 10 internship; AECHS - 44 pre-college, 15 internship)
Internship | 15 internship spots secured |  | 2013-06-14 |  | Owner | Met score card goal |  | Aligns to College Report Card goal: Partnerships numbers will increase annually by 10% (AFBHS - 17 pre-college, 10 internship; AECHS - 44 pre-college, 15 internship)
ALL | Summer Programs Update #5 | Data share | 2013-07-08 |  | Owner | Ready/executed on time | Update is sent by email to all stake-holders with glows, grows, calendar look-ahead, and data | Content specs.: comprehensive scholar-by-scholar data on which scholars submitted applications to which programs; comprehensive data on current eligibility for each program tier (current circa QII); pre-college acceptances and financial aid awards run-down to date by scholar; internship secured spots update; internship and growth program placements; Summer Academy programs run-down; matriculation and participation update
Pre-College | Day prior to departure phone calls to families completed | Communication | 2013-07-15 |  | Owner | Ready/executed on time | Every scholar departing for a pre-college program gets a check-in call home the day before they depart for their program to ensure all logistics are still in place and that there are all-systems-go. | If the Owner is on vacation, they need a fill-in to do this.
Pre-College | Weekly check-in phone calls to pre-college scholars | Communication | 2013-07-30 |  | Owner | Ready/executed on time | Each scholar calls to check in weekly with the Owner. | The school should have some sort of point of accountability on this.
Internship | Bi-weekly site manager check-in phone calls/emails for internship placements | Communication | 2013-07-30 |  | Owner | Ready/executed on time
ALL | Summer Programs Update #6 | Data share | 2013-08-02 |  | Owner | Ready/executed on time | Update is sent by email to all stake-holders with glows, grows, calendar look-ahead, and data | Content specs.: comprehensive scholar-by-scholar data on which scholars submitted applications to which programs; comprehensive data on current eligibility for each program tier (current circa QII); pre-college acceptances and financial aid awards run-down to date by scholar; internship secured spots update; internship and growth program placements; Summer Academy programs run-down; matriculation and participation update
ALL | 75% of scholars who do not complete or miss their pre-assigned summer programs will attend the make-up summer program boot camp | Workshop | 2013-08-16 |  | Owner | Met score card goal | All scholars who fail to compete their summer program will participate in an 80-hour make-up opportunity. | Aligns to College Report Card goal: 75% of scholars who do not complete or miss their pre-assigned summer programs will attend the make-up summer program boot camp
ALL | Update bulletin boards for incoming students with summer programs hilights | Hype Event | 2013-08-22 |  | Owner | Ready/executed on time
ALL | Summer Programs Update #7 | Data share | 2013-08-30 |  | Owner | Ready/executed on time | Update is sent by email to all stake-holders with glows, grows, calendar look-ahead, and data; this is the FINAL REPORT for Summer Programs 2012-13. | Content specs.: comprehensive scholar-by-scholar data on which scholars submitted applications to which programs; comprehensive data on current eligibility for each program tier (current circa QII); pre-college acceptances and financial aid awards run-down to date by scholar; internship secured spots update; internship and growth program placements; Summer Academy programs run-down; matriculation and participation update
ALL | 100% of scholars receive a rating of “satisfactory” or “highly satisfactory” when evaluated by pre-college or internship placement | Review | 2013-08-30 |  | Owner | Met score card goal |  | Aligns to College Report Card goal: Top quartile will participate in a pre-college program or highly selective internship
ALL | 100% of sites agree to following year placement on end of summer survey | Review | 2013-08-30 |  | Owner | Met score card goal |  | Aligns to College Report Card goal: Top quartile will participate in a pre-college program or highly selective internship
Pre-College | Pre-College Debrief and Thank You's Workshop | Meeting-mandatory | 2013-08-31 |  | Owner | Ready/executed on time
Internship | Internships Debrief and Thank You's Workshop | Meeting-mandatory | 2013-08-31 |  | Owner | Ready/executed on time
Note on J23: Megan Fraker: Is this where links to better lesson will go? Or pu tfile names where they can find the docs?

## 2011-2012 Goals
Metric | Goal | Notes
% of scholars who complete summer programs | 100%
# of eligible scholars who complete pre-college programs | 30
# of juniors who matriculate at pre-college programs | 15 | Estimate
# of sophomores who matriculate at pre-college programs | 15 | Estimate
# of freshmen who matriculate at pre-college programs | 0 | Estimate
# of eligible scholars who complete internships | 30
% of eligible scholars who complete a growth program, who are not in a pre-college program or internship | 100%
% of Summer Academy scholars who complete a growth program or on-campus program | 100%
% of scholars completing pre-college programs | 15%
% of scholars completing internships | 20%
% of scholars completing growth programs | 50%
% of scholars completing Summer Academy Afternoon Enrichment | 15%
% of scholars completing an Summer Opportunities program | 100%

## Roles & Responsibilities
Summer Programs Owner | Summer Programs Approver (Dean) | AF through College Network Support coach | School Ops. team
Ownership of planning and execution of project plan (calendar, deliverables, logistics) | Providing whole-school academic/character data to SD at each PR and guiding eligibility process and messaging for pre-college, internship and growth opportunities | Liaising with IHDF to secure internships | Processing all payments per requests from Dawson only
Communications to staff, parents, scholars about optional & mandatory events | Liaising with AF Brooklyn boards to secure internships | Setting summer programs placement goals | Ordering any books per requests from Dawson only
Calendaring, planning, running, and follow-up for all optional/mandatory meetings, workshops, and other events | Liaising with Network Support to secure internships | Measuring team's success against goals and metrics on monthly basis | Arranging and invoicing for travel per requests from Dawson only
Designing and updating all bulletin boards and other student communication tools with exciting updates that invest scholars in summer programs | Hiring program leaders for on-site programs | Supporting and trouble-shooting on ad hoc basis as unanticipated questions/problems arise | On-campus program logistics support per requests from Dawson only
Coaching the development of, editing, and signing off on all applications | Setting 2012 summer programs budget
Submission of any and all applications | Coaching around workshop and meeting structures, agendas, lesson plans, presentations, etc.
Reviewing, processing and submitting any and all matriculation documents | Providing feedback on and signing off on all summer programs policies
Tracking all payments and communicating all payment requirements and timelines to Ops. | Providing keep program leads and connecting Dawson with existing partners
Uploading any and all program app. Or matriculation form documents to Naviance | Approving program partners and individual placements
Posting all applicant materials to Naviance | Advising on and approving grants distribution strategy
Owning and running all check-ins on summer programs | Providing feedback on all collateral, events, etc.
Tracking all summer programs data and sharing data with VCJ as scheduled | Reviewing bi-monthly data and sharing with Network Support
Drafting all summer programs related policies; posting all finalized policies to Naviance | Auditing Naviance uploads of applications, letters of recommendation, CSAs, resumes, personal statements, etc.
Owning all matriculation logistics, delegating to Ops. team as appropriate | Providing feedback and support based on regular analysis of placement data
Orchestrating teacher recommendation solicitation process and holding teachers accountable for submitting high quality, on-time recs.
Outreach to pre-college, formalized City-wide internship, and growth program partners
School's first point of contact for all programs (pre-college, internship, growth)
Interfacing with all parents on summer programs related questions and requests
Owning summer programs ops. during summer months: weekly check-ins, matriculation confirmation, trouble-shooting situations
Orchestrating grants process for pre-college scholars
Facilitating PID conversations for scholars who do not complete their summer program requirement
Keeping all financial records organized in College Office
Delegating any and all appropriate work to Team Ops.
Note on D2: Megan Fraker: I think it makes sense to change all the names to the name of the role (such as SP Owner instead of "Dawson" and SP Approver instead of "VCJ"