## Key Planning Steps & CFS
Readiness Planning Process: Key Steps + CFS
Planning Steps
1. Develop Clear Roles & Responsibilities for Principal and Planning Partner
2. Determine a regular check-in time and structure for Principal and Planning Partner
3. Decide on a template to use for your readiness project plan (see the CFS below & tabs in this workbook for whole-LT plan and individual LT member plans)
4. Plot out who, when, and how to complete the readiness project plan (auditing current plans for quality, determining degree of change for each plan, etc.)
5. Determine the role and allocation of LT time, dean coaching meetings, and half-day PD time for readiness work
6. Determine and build your knowledge capture system for readiness plans (Many Minds, Google Drive, etc.). Share this with your Regional Supt.
Pre-planning Reflection Questions
*What adaptive challenges could we face? (e.g. how much will we engage/trust our staff to shape change; how will we bring D&I lens to planning process; what is the talent landcape going into this work both in terms of returning vs transitioning staff, and transitioning LT members?)
*What technical challenges could we face? (e.g. process that isolates plans rather than considering interconnectivity, not dedicating enough LT time to readiness)
*How will we audit the quality of our current plans? (e.g. will we engage staff in this auditing to identify broken windows?)
*What structures will we dedicate time within to engage staff on readiness? (e.g. Friday PD, separate meetings, August Teacher Training, etc.)
Possible Principal R&R
* Co-develop readiness project plan with planning partner
* Drive vision for the next school year
* Create core readiness docs, or delegate to LT members
* Give input and feedback on delegated readiness docs
* Facilitate or delegate facilitation of readiness convesrations with LT or staff
Possible Planning Partner R&R
* Co-develop readiness project plan with planning partner and own maintenance and updating of project plan
* Keep LT on track to meet deadlines in project plan (e.g. create shared tracker, collect drafts, follow up on uncompleted work)
* Coordinate deadlines and due dates for readiness docs and accountability structures
* Calendar LT Meetings, PD, and teacher input groups on readiness docs; send relevant calendar invites & communication
* Create & Maintain knowledge management base on Many Minds / Google Drive
* Coordinate with principal to ensure strong agenda setting for readiness conversations, from LT meetings to staff input conversations
CFS: Principal - Planning Partner R&R
*Planning Partner and Principal own distinct responsibilities in planning process and are clear on these responsibilities
*Regular touchpoints are scheduled for alignment
CFS: Master Readiness Plan
*Scope extends beyond network-produced guidance to include school specific readiness plans (e.g. adult culture vision, communication structures)
*Current quality of plan (strong, needs revision, etc)
*School action (e.g. Internalize FOI / Operationalize Behavior Policy / Update HW System / Build Summer PD Agenda)
*Dates for release of relevant guidance from Network Support
*Due dates for input, draft plan, and final plan (these should be backwards mapped from roll-out to staff in August PD and key cohort workshopping deadlines shared by Regional Supts )
*Status of current document
*Owner
*Stakeholders or input groups
*Priority or degree of change
*Links to or naming of where to upload/access relevant materials
CFS: Individual Leader Readiness Plan
*Contains each readiness plan that LT member owns
*Anticipated size of lift / time allocation
*Place to capture input gathered throughout process or questions/info needed from others
*Optional: Includes time allocation for providing input on other plans where LT member is primary input/feedback provider
CFS: Knowledge Management Plan
*The LT, RDO, and Regional Supt are aligned on a single place where readiness documents will live, as well as norms for uploading, review, and marking as final.
*The responsibilty of uploading documents and maintaining the site is assigned to one or more people

## LT Readiness Project Plan
Guidance Document | Link to or name of folder on Many Minds/ Google Drive for posting | Degree of Anticipated Change from 2015-16 Network Guidance | Priority (1-5) | Current Quality (1-5) | Change Needed (0-5) | NS Recommended School Owner | Primary Input Group | Secondary Input Group | School Action (Build / Operationalize / Internalize / Revise) | Status | Network Guidance Published | Primary Input Due | Internal First Draft Due to MM/Google Drive | Feedback Provided & by whom | Secondary Input Due | LT Alignment | Final Draft Posted | Tier 1 docs sent to Regional Supt & NS [DO NOT EDIT] | Core or Consistent [Consistent = No modification: Internalize & Operationalize]
Links / Additional Info | Put main hub link here | How much will the guidance NS shares look different from NS's 15-16 guidance? | H / M / L | 5 = Highest | 5 = Overhaul | Replace with your school owner | e.g. LT member name | e.g. GLC's; Whole staff | NS recommendation here | Where is the 16-17 plan in the process? (e.g. Not Started - First draft posted - Final) | Readiness Hub Link | By when do you receive your first round of input? |  | Who provides feedback on Draft 1, and by when? | By when do you receive your second round of input? | When does the LT align on the final plan? | RS & RDO should have access to this site | RS may request add'l docs
Schedule & Staffing (including Academy Level Program Summary) |  | ES - Moderate MS/HS - Minimal |  |  |  | Principal |  |  | Build from NS model |  | 2016-02-05 | [6 empty] | 4/4 first draft 5/2 second draft | Core
AF Summer PD High Level Calendar |  | Moderate |  |  |  | Principal |  |  | FYI / Internalize |  | shared in cohorts by 2/5/2016 | [7 empty] | Consistent
Co-Teaching Guidance |  | Minimal |  |  |  | SSL |  |  | Revise if needed |  | 2016-02-12 | [7 empty] | Core
Attendance System |  | Minimal (Legal only) |  |  |  | Principal + DSO |  |  | Revise if needed |  | 2016-02-12 | [7 empty] | Consistent (for legal considerations)
Parent Info Sessions |  | Republishing |  |  |  | Principal + DSO |  |  | Revise if needed |  | 2016-02-12 | [7 empty] | Core
Parent Orientation |  | Republishing |  |  |  | Principal + DSO |  |  | Revise if needed |  | 2016-02-12 | [7 empty] | Core
Family Agreements, Chats, Recommitment Meetings |  | Republishing |  |  |  | Principal + DSO |  |  | Revise if needed |  | 2016-02-12 | [7 empty] | Core
School Priorities for 2016-17 |  | Moderate |  |  |  | Principal |  |  | Build from NS model |  | 2016-03-11 | [6 empty] | 2016-05-09 | Core
TIR Program Design |  | Minimal |  |  |  | Principal |  |  | Operationalize |  | 2016-03-11 | [7 empty] | Core
School Culture Guidance (Common Picture, Investment Plan, etc) |  | Minimal |  |  |  | Principal + DOS |  |  | Revise if needed |  | 2016-03-11 | [7 empty] | Core
Behavior Policy & Behavior Intervention Plan |  | Moderate |  |  |  | Principal + DOS (In some cases, SSL) |  |  | Revise if needed |  | 2016-03-11 | [7 empty] | Consistent
Dean Management Guidance (Dean Management Plan, New Dean Learning Plan, Coaching Expectations, LT R&R, Meeting Matrix, Coaching Plan for Deans, etc.) |  | Significant - Will include new guidance and emphasis on CFS |  |  |  | Principal |  |  | Build from NS model |  | 2016-03-11 | [6 empty] | 2016-05-23 | Core
Program Overview (interventions embedded) |  | Varied |  |  |  | Principal + AD |  |  | Internalize |  | 2016-03-11 | [7 empty] | Consistent
FOI's & FOI Look-For Documents |  | Varied |  |  |  | Principal + AD |  |  | Internalize |  | 2016-03-11 | [7 empty] | Consistent
Scopes & Sequencces |  | Varied |  |  |  | Principal + AD |  |  | Internalize |  | 2016-03-11 | [7 empty] | Consistent
Independent Reading Goals & Plan (by academy level) |  | ES - Significant MS/HS - Republishing |  |  |  | Principal + AD |  |  | Operationalize |  | 2016-03-11 | [7 empty] | Core
Homework System & Overview of HW expectations across contents |  | Minimal |  |  |  | Principal + AD |  |  | Revise if needed |  | 2016-03-11 | [7 empty] | Core
Family Handbook |  | Moderate |  |  |  | Principal + DSO |  |  | Revise |  | 2016-03-31 | [7 empty] | Consistent
Teacher Development Plan Part 1 (including Early Dismissal PD Plan) |  | Moderate |  |  |  | Principal |  |  | Build from NS model |  | 2016-04-15 | [7 empty] | Core
Weekly Staff Memo |  | Republishing |  |  |  | Principal |  |  | Revise if needed |  | 2016-04-15 | [7 empty] | Core
Social Worker/Counselor R&R |  | Minimal |  |  |  | Principal |  |  | Operationalize |  | 2016-04-15 | [7 empty] | Core
Summer Homework (NEW for 16-17) |  | New |  |  |  | Principal + AD + DSO |  |  | Operationalize |  | 2016-04-15 | [7 empty] | Core
Regional Calendars |  | TBD |  |  |  | Principal + DSO |  |  | Determine school-specific dates |  | 2016-05-05 | [7 empty] | Consistent
Mandated Reporting |  | Minimal or Republishing |  |  |  | SW/C or DOS |  |  | Operationalize |  | 2016-05-13 | [7 empty] | Consistent
Teacher Development Plan Part 2 (including Teacher R&R) |  | Moderate |  |  |  | Principal |  |  | Operationalize |  | 2016-05-13 | [7 empty] | Core
Lesson Planning Expectations & Plan |  | Moderate |  |  |  | Principal + AD |  |  | Operationalize |  | 2016-05-13 | [7 empty] | Core
School Culture Start of Year Plan |  | Minimal |  |  |  | Principal + DOS |  |  | Operationalize |  | 2016-05-13 | [7 empty] | Core
School Summer PD Plan |  | Moderate |  |  |  | Principal |  |  | Build from NS model |  | 2016-06-10 | [7 empty] | Core
Special Services Compliance & Practices |  | Minimal to Moderate |  |  |  | SSL |  |  | Operationalize |  | 2016-06-10 | [7 empty] | Consistent

## Indiv. Leader Readiness Plan
Guidance Document | Priority (1-5) | Current Quality (1-5) | Change Needed (0-5) | Approx. Time Allocation | Network Guidance Published | Primary Input Group | Primary Input Due | Internal First Draft Due to MM/Google Drive | Feedback Provided & by whom | Secondary Input Group | Secondary Input Due | LT Alignment | Final Draft Posted | Info needed from Network | Info needed from Principal | Info needed from other LT members / others
Links / Additional Info | H / M / L | 5 = Highest | 5 = Overhaul | # Hours of expected work | Readiness Hub Link | e.g. LT member name | By when do you receive your first round of input? |  | Who provides feedback on Draft 1, and by when? | e.g. GLC's; Whole staff | By when do you receive your second round of input? | When does the LT align on the final plan? | RS & RDO should have access to this site | What additional info do you need to prepare this plan? | What additional info do you need to prepare this plan? | What additional info do you need to prepare this plan?