## IR Launch Project Plan - DSO
Update 4/19: A resource for determining the lexile level of a scholar based on STAR data is now available on the "List of Resources" tab. Update 4/5: In training academic leaders, a great question was raised. Some schools do not F&P test every 3rd & 4th grader. Therefore, there will be some schools who do not have F&P/STEP levels for every scholar. In this case, the lexile level should be used in place of F&P/STEP level so scholars can ID appropriate books for them. It is important that, if this is the case, you label your Gr 3-4 books and bins by Lexile Level. (They can also be labeled by F&P level, but lexile level will be critical.) The Lexile level is assessed via the fluency screener, and therefore all Gr 3-4 scholars will have a lexile level on record. See the resource tab for a link to a conversion chart that you can use to determine F&P/STEP and lexile level correspondence. Next Step for DSO's of schools with Grades 3-4: Check with your principal or dean to determine whether you should (1) place your book order to label books used in Gr 3-4 by lexile level in addition to F&P level, or (2) adjust any already-placed book order to include labeling books by lexile level if it does not already. (Note: Lexile level was already a recommended book label on the google doc for placing Booksource orders.) Middle Schools already use lexile levels, so as scholars transition from Gr 4 to Gr 5, they will continue to use their lexile level to identify books on their reading level. Reach out to Marissa Siefkes with any questions.
Action | Category | Date | Owner | Additional Notes
Determine budget for IR launch | Library Setup | 2016-03-01 | DSO | Launch schools have a budget target of $60k within their 7203 budget line target for this work
Determine your IR library vision of excellence: % of fiction vs non-fiction; levels and proportion of levels; # of unique titles | Library Setup | 2016-03-11 | DSO + Principal/AD | Strong IR Library has approx 50/50% split fiction/non-fiction, and enough unique titles so that books can rotate throughout the year and scholar always has option of a fresh text.
Assess current classroom library book inventory (use questions to right) | Library Setup | 2016-03-21 | DSO + Principal | Assess: 1. # of books at each level 2. percentage of those that are unique titles (you'll want enough unique titles so that fresh titles are available at each level each week - see row 6 for ways to achieve this) 3. # of fiction vs non-fiction books (aim for as close to 50/50% as possible) 4. labeling of books - are they labeled by F&P/STEP and (in Gr 3-4) Lexile level already? 5. organization of books - are they organized by F&P level and, ideally, into fiction/non-fiction bins?
Determine approach to outfitting IR libraries by making decision to supplement current book inventory or order new, complete libraries (see recommendations to right) | Library Setup | 2016-03-23 | DSO + Principal | Option 1: If during the inventory process you find your current books provide a strong start toward your vision for level and fiction/non-fiction allocation, and that your library is already labeled and organized by level, we recommend you order supplements to round out your library. See Recommended Vendors tab for full detail. Option 2: If not (and we anticipate most schools will be in this category), we recommend ordering new, complete libraries from one of our vendors. See Recommended Vendors tab for full detail.
Determine your critera for book ordering based on your vision of excellence and (if going with Option 1 of supplementing texts) your current inventory of books. | Library Setup | 2016-03-24 | DSO + Principal/AD | Strong IR Library has approx 50/50% split fiction/non-fiction, and enough unique titles so that books can rotate throughout the year and scholar always has option of a fresh text. See 1b at the link below for a way to calculate # of books to order per grade per level, based on their incomping reading level and how quickly scholars move through books in each grade. https://manyminds.achievementfirst.org/sites/NetworkSupport/AcademicOps/ReadinessHub/Shared%20Documents/Independent%20Reading%20Plans/IR%20Library%20Training_Resources_FAQ.docx One option to ensure fresh titles is to order a certiain number of unique titles per level per grade, place a third in each of 3 sections, and rotate the books between sections in November and March. Consider how to move titles from one grade down to another.
Contact book vendor to create initial order (If you want to include bin orders at this time, take the steps in rows 13-14 first) | Library Setup | 2016-03-25 | DSO | See Recommended Vendors tab for full detail on both options available.
Receive initial book list from vendor | Library Setup | 2016-04-06 | DSO
Vet book order list with AD | Library Setup | 2016-04-08 | DSO + AD
Adjust book order list and place final order | Library Setup | 2016-04-11 | DSO
Identify space in each classroom for library, in conjunction with DOS/Principal | Library Setup | 2016-04-01 | DSO + Principal | Consult with DOS/Principal about vision for library, where scholars sit during IR how they should access library. It is important that the library is easily accessible for scholars and there is sufficient space for each level to have a fiction & non-fiction bin at minimum. It is more important to prioritize easily-accessed bookshelves for IR Libraries than for Guided Reading books. If your school has a book room, you may want to consider moving Guided Reading books out of classrooms to free up space for IR libraries. See check-list for library set-up: https://manyminds.achievementfirst.org/sites/NetworkSupport/AcademicOps/ReadinessHub/Shared%20Documents/Independent%20Reading%20Plans/ES%20IR_ClassroomLibraryChecklist.docx
Determine system for organizing books within library | Library Setup | 2016-05-01 | DSO | See check-list for library set-up: https://manyminds.achievementfirst.org/sites/NetworkSupport/AcademicOps/ReadinessHub/Shared%20Documents/Independent%20Reading%20Plans/ES%20IR_ClassroomLibraryChecklist.docx. Bins must be labeled by F&P & corresponding Lexile Level*; Recommend one clearly-labeled fiction and one non-fiction bin by level. For a truly exemplar library, you would have several additional organizational components: within fiction & non-fiction division, further bins to sort books by high-interest topics, such as "weather" or "animals." Alternatively, there would be a bin of "high interest" books. Scholars could select occasionally from this even if it is outside of their reading level.
Determine system for scholars returning books (may impact what you order/setup) | Library Setup | 2016-05-01 | DSO + AD | Consider having two "return" bins so books don't get mis-binned up as they go back into the library
Project plan physical library setup | Library Setup | 2016-05-01 | DSO
Designate dates and times of day for each component of work: book triage, book labeling (if needed), bookshelf setup, bin unpackaging and labeling, label printing | Library Setup | 2016-05-01 | DSO | Consider using Friday PD remaining in school year
Determine # of bookshelves and bins needed for standard setup across all libraries | Library Setup | 2016-05-31 | DSO
Determine how you will make the library a sacred, appealing, magical place. | Library Steup | 2016-06-03 | DSO | In the IR library, a scholar should feel the feeling we have when we enter a beautiful library or bookstore. It should feel like the most sacred and magical space in the classroom. There should not be chromebooks nearby (we do not use Accelerated Reader during IR because we want scholars spending their time uninterrupted in texts). There should not be tattered books. See check-list for library set-up (link below), as well as photo exemplars in the IR Google Drive linked in the "List of Resources" https://manyminds.achievementfirst.org/sites/NetworkSupport/AcademicOps/ReadinessHub/Shared%20Documents/Independent%20Reading%20Plans/ES%20IR_ClassroomLibraryChecklist.docx
Order bookshelves, bins, labels, and aesthetic decorations | Library Setup | 2016-06-17 | DSO / SSM | Consider your ops/facilities readiness timeline when determining order date and delivery
Scope out human capital needed - existing and temp resources | Library Setup | 2016-06-17 | DSO
Vet and hire required temps and set up payment systems | Library Setup | May-July | DSO
Train temps on book labeling and how to distinguish book level | Library Setup | May-July | DSO | Books should be labeled with F&P & (in Gr 3-4) Lexile Reading Levels. You can use Scholastic App or Booksource Classroom Organizer App (links on "List of Resources" tab) to determine level of a book. You can also use the F&P/STEP/Lexile Level conversion chart (link on "List of Resources" tab). Books should NOT be labeled with genre or fiction/non-fiction because we want scholars to engage in the independent thinking required to categorize the text when selecting it. It is not necessary to remove fiction/non-fiction or genre labels from books you are reusing from previous years, however.
Ensure all "deceased" books and Reading A-Z books are removed from classroom library text that will be used in the IR library | Library Setup | May-July | DSO | Guided reading books should only appear in libraries IF AND ONLY IF the scholar has just finished the book in IR. We want to encourage scholars to re-read texts they are interested in, so teachers are encouraged to place one to several copies of a guided reading book in the IR bins right after instruction for that book is finished.
Label all books not yet labeled | Library Setup | June/July | Ops Team / Temps | See sample book labels here (NOTE: These do not include lexile level*): https://manyminds.achievementfirst.org/sites/NetworkSupport/AcademicOps/ReadinessHub/Shared%20Documents/Independent%20Reading%20Plans/BookLabels.docx
Label all book bins | Library Setup | June/July | Ops Team / Temps | See sample bin labels here (NOTE: These do not include lexile level*): https://manyminds.achievementfirst.org/sites/NetworkSupport/AcademicOps/ReadinessHub/Shared%20Documents/Independent%20Reading%20Plans/Independent%20Reading%20Level-%20Bin%20Labels.docx
Determine whether to put books in labeled bins first, then deliver to libraries, or put bins in libraries first, then fill with books | Library Setup | June/July | DSO
Have bookshelves placed in classroom libraries | Library Setup | June/July | DSO | Consult AD to determine any edits to Thinking by Genre poster at link below https://manyminds.achievementfirst.org/sites/NetworkSupport/AcademicOps/ReadinessHub/Shared%20Documents/Independent%20Reading%20Plans/Thinking%20Jobs%20by%20Genre%20Poster.docx
Print & hang genre based thinking posters in libraries | Library Setup | June/July | DSO/SSM
Design book baggie system, show draft to AD, finalize together | Book Baggie Setup | 2016-06-03 | DSO; Consult AD | See sample baggie image at link below and more resources on book baggie systems in IR Google Drive linked in the "list of resources" tab. https://drive.google.com/a/achievementfirst.org/file/d/0B-GcMNsXPnIBZzV6WHNMTFdBZFk/view
Order bags | Book Baggie Setup | May-June | DSO / SSM | For bag size, keep in mind # of books a child should have in book baggie at a time (K= 8-12; 1 = 6-10; 2 = 8-10; 3 & 4 = 4-6)
Project plan bag labeling | Book Baggie Setup | 2016-06-10 | DSO
Scope out human capital needed - existing and temp resources | Book Baggie Setup | 2016-06-10 | DSO
Designate dates and times of day for book baggie system setup | Book Baggie Setup | 2016-06-10 | DSO
Vet and hire required temps and set up payment systems | Book Baggie Setup | June/July | DSO
Create plan for every scholar to have an IR folder, show draft of folder to AD, finalize together | IR Folder Setup | 2016-06-10 | DSO; Consult AD
Order folders | IR Folder Setup | June/July | DSO
Design how you'll have every scholar's IR folder delivered to classrooms, labeled with their name | IR Folder Setup | 2016-06-10 | DSO
Print IR graphic organizers and exit tickets, working with AD to get those templates | IR Folder Setup | June/July | DSO
Create calendar of book rotations across sections/grades based on your strategy for maintaining fresh titles in each classroom. | Library Maintenance | July | DSO | Suggestion is to place one third of titles in each classroom and rotate in November and March
Determine owner & system for book maintenance (e.g. if a book's label comes off, needs to be replaced, etc) | Library Maintenance | July | DSO | Consider periodic triage of library to re-organize any mis-binned books, as well as remove and repair damanged books. One option for the latter is teacher maintenance of a "book hospital" bin where students place books with damage.
All Book Baggies created and in classrooms | Book Baggie Setup | 2016-08-01 | DSO
All IR Folders created and in classrooms | IR Folder Setup | 2016-08-01 | DSO

## Recommended Vendors
| Booksource A larger-scale book vendor specializing in classroom library build-out that has worked with many of our schools. | Bank Street Schoolbooks A smaller-scale book vendor affiliated with the Bank Street College of Education that has worked with our Network Support ES ELA Team and several AF schools.
Website | http://www.booksource.com/ | http://www.bankstreetbooks.com/schoolbooks
Contact Info | NY: Sean Binkley ¦ sbinkley@booksource.com and Stephanie Schwab ¦ sschwab@booksource.com CT & RI: Julie Allen ¦ julie.allen@booksource.com | Caitlyn Hodges-Morrissey ¦ cmorrissey@bankstreet.edu ¦ 212-281-8101
Pros | *Builds library according to criteria, rather than you dictating titles *Free labeling of texts with F&P level & Lexile Level (and up to 2 other select labels) *Discounts/freebies on shelf and storage bins with qualifying orders *NY: Can generate list using only FAMIS titles and produce FAMIS code for use on DOE shopping site | *High-quality vetted book list, already created *Delivery in NY comes with option to have moving company deliver books straight to classrooms
Potential Cons | *List not pre-built (though you could use Bank Street list as a starting place) *Up to two-week turnaround to receive initial book list | *Smaller vendor *Shipping to CT & RI may be more expensive *Book labeling of F&P level & Lexile Level available at 3% of total order cost
Process for Ordering | Pre-Step: Determine whether you will build full libraries from scratch, or supplement existing libraries.
| 1. Provide Booksource with criteria for your library build via this workbook. Email the contact in your region (row 3) to share that your order information is ready to go. Workbook link: https://docs.google.com/spreadsheets/d/1GZytz6f9wwk2yQwvVSSlueyosZJfr5chcznl6SAwMT8/edit#gid=0 | 1. Examine the book list that Bank Street created for us. Vet this list with your instructional leaders, and edit the list to indicate the titles and quantities you would like to purchase. Book list link: https://drive.google.com/a/achievementfirst.org/folderview?id=0B-GcMNsXPnIBc3JsS052QUNQVEk&usp=drive_web
| 2. Booksource will email you an intial list (NY Schools can elect to have a list with FAMIS-approved titles only) | 2. Contact Caitlyn Hodges-Morrissey to request quote based on edited book list (you can also ask her to tailor the list based on certain criteria - e.g. X titles at X F&P/lexile level, 50% fiction/nonfiction, and generate a quote based on her revisions).
| 3. Vet the list with your instructional leaders & send back any adjustments to Booksource | 3. Optional (If Caitlyn is revising the list on criteria) - Vet revised list with instructional leaders & send back any adjustments to Caitlyn
| 4. Send back any adjustments to Booksource | 4. Bank Street generates quote based on book list and desired bins/storage containers
| 5. Optional - Do another round of book list review | 5. Determine how you'd like books packaged and shipped. Booksource can package books by classroom, down to individual bins.
| 6. Booksource generates quote based on book list and desired bins/storage containers | 6. Place purchase order with packaging and shipping instructions
| 7. Determine how you'd like books packaged and shipped. Booksource can package books by classroom, down to individual bins. | 7. Place purchase order with packaging and shipping instructions
| 8. Place purchase order with packaging and shipping instructions (include bins, materials you want to order through this vendor as well) | 8. NY Schools Only: Booksource will provide FAMIS collection code - this will require a few days to be approved, and then books will show up in ShopDOE.
| 9. NY Schools Only: Booksource will provide FAMIS collection code - this will require a few days to be approved, and then books will show up in ShopDOE. | 9. Process invoice for book order
10. Process invoice for book order
Notes | *All orders will receive up to 4 free labels. For IR libraries, books must be labeled with F&P level. Books should not be labeled fiction/non-fiction. *Every $500 spent will qualify for a free blue bin and every $10k will get 5 clear sterilite tubs to make organizing and storing the books easier. *Shipment window from time of final purchase order: 3-6 weeks | *Book labels for F&P level can be generated and sent with books, or placed on books prior to shipmnet; cost is 3% of total order price *Shipment window from time of final purchase order: approx. 8 weeks

## List of Resources
Link to Resource | Resource
Link to IR Google Drive | Resources for every component of IR Library planning, from exemplar photos to how-to guides, to training plans and lesson plans
Resources from 3.30 DSO Training | *UPDATED 4.5* Notes & Recording from 3.30 DSO Training on IR Library Launch
IR Kick-Off Guide | Details rational for and components of effective IR, how to set up schedule and staffing to support IR, and how to prepare for the flow and logistics of the IR block
Sample order from Booksource | AF Brownsville ES's book order
Bank Street Independent Reading Book List | Classroom Library list that Bank Street Library created for us - includes fiction and non-fiction titles by grade and level.
Classroom Library Checklist | A checklist for library access/organization to set up your library to create a culture of reading.
Exemplar Library Photo | Photo of exemplar library organization - labels and bins.
Sample Graphic Organizer | Sample graphic organizer for scholar to record key components of a text while independently reading.
Thinking by Genre Poster | Poster to hang in classroom library.
Sample Book Labels | Template for book labels by reading level.
Sample Bin Labels | Template for book bin labels by reading level and fiction/non-fiction. Includes return bin label.
Exemplar Book Shopping Plan | Elm City College Prep Elementary's book shopping plan
Independent Reading FOI Look-For | *NEW 4.15* Fundamentals of Instruction for the IR block.
Scholastic App for book leveling | App to use to identify level of titles in your library.
Booksource Organizer App | App to use to identify level of titles in your library.
F&P/STEP/Lexile Level Conversion Chart | *NEW 4.5* Conversion chart of F&P, STEP and Lexile Levels.
STAR/Lexile Level Conversion Guide | *NEW 4.19* Guide to find Lexile Levels based on STAR data.

## IR Launch Checklist - SLT
Action | Category | Date | Owner | Additional Notes
Set up schedule & staffing to support IR |  |  | Principal w/ DSO
Select IR graphic organizer / exit ticket that will be used in each grade |  |  | AD or lead teacher
Set expectations for teachers grading IR graphic organizers/exit tickets |  |  | AD
Develop a vision for where/how scholars should sit during IR |  |  | DOS
Design book shopping routine |  |  | DOS
Create lesson to teach the "shopping for books" routine |  |  | AD
Identify date to train IR teachers on the launch |  |  | AD + Principal
Train teachers prior to IR launch |  |  | Principal or AD | See training guide tab
Identify IR roll out date with scholars (first day of IR) |  |  | AD + Principal
Stamina build up timeline: Identify date by which all scholars should be reading for minimum # of min daily |  |  | AD
If applicable: Identify date when K-2 Cap Teacher will return to teaching GR (instead of working on strong IR launch) and clear expectations for launching both GR and IR simultaneously |  |  | AD + DOS
Determine who is responsible for crafting IR lesson plans (shared across K-4 vs written by 1 person per grade, etc) and their due dates |  |  | AD
Post IR Expectations |  |  |  | AF Endeavor ES example expectations: - Voices off (picture of lips zipped) - Books flat (picture of book no table) - Eyes on your book (picture of eyes with arrows to book) - Think about what you are reading (picture of kid reading with thought bubble and thinking/question stems)
Identify who will review IR launch lesson plans and due dates for these lesson plans; ensure LP's are reviewed for elements of the "week 6 vision" |  |  | Principal
Observation, Real-Time Coaching, Walk Thru Plan of Action for LT during IR launch weeks and after the launch |  |  | Principal
Optional: Create Homework Reading Log and Family Accountability/Follow-up Systems |  |  | DOS
Optional: Training session for families on the value of IR and looking out for fake reading behaviors at home |  |  | DOS
Optional: Design vision and system for grade wide OR school wide IR competitions to hype IR |  |  | AD

## Teacher Training Guide
PD Session for Teachers | Approx. Min | Owner
Overview: Purpose of IR, Value of IR, Beliefs around IR, Flow of the Block | 30 min
Roll Out Speeches: Watch videos, Craft speeches, Rehearse speeches | 60 min
Book Shopping Routine: Vision and How to Teach it | 20 min
Teacher Role During IR: Watching Out For and Addressing Fake Reading Behaviors | 30 min
Lesson Planning and Rehearsing First Day Lessons | 40 min* Document says hour - should this be hour?
**Ideally each session would be longer. Need minimum 3 hours total for this.